Documento Maestro de Producto

Plataforma Inteligente de Control de Proyectos, PMO, BPM, Presupuesto, Riesgos, Comunicación, Documentos, Materiales e Integración ERP

Versión de revisión conceptual

| Elemento | Descripción |
| --- | --- |
| Nombre conceptual | ProjectOps360° |
| Propósito | Definir todos los módulos de una plataforma que controle proyectos de forma profesional, conectando metodología de Project Management, BPM, comunicación, cambio, documentos, budget, riesgos, inventario, ERP y AI. |
| Principio base | Cada tarea, comunicación, documento, riesgo, cambio, decisión, costo y material debe quedar conectado y trazable. |
| Etapa actual | Definición funcional del producto antes de crear el prompt final de desarrollo. |

# Tabla de contenido

- 1. Visión general del producto

- 2. Principios de diseño

- 3. Arquitectura funcional general

- 4. PMO / Portfolio Management

- 5. Project Charter e Initiation

- 6. Stakeholder Management

- 7. Communication Plan Management

- 8. Communication Intelligence Hub

- 9. Document Control

- 10. Change Control

- 11. Task & Schedule Management

- 12. Budget Management

- 13. Risk Management

- 14. Issue Management

- 15. BPM / Process Improvement

- 16. Materials & Inventory Management

- 17. ERP Integration Layer

- 18. Reports & Dashboards

- 19. AI Super Project Manager

- 20. Security, Roles & Permissions

- 21. Database Structure

- 22. MVP Roadmap

- 23. Navegación y UX

- 24. Decisiones pendientes antes del prompt final

# 1. Visión general del producto

La plataforma propuesta no debe competir con Asana, Trello, Monday o ClickUp como un simple gestor de tareas. Debe posicionarse como un sistema operativo de proyectos: una herramienta para controlar proyectos completos con metodología profesional, trazabilidad, presupuesto, riesgos, comunicación, documentos, procesos, materiales, ERP y AI.

La promesa central del producto es:

Controlar proyectos como una PMO profesional: desde el charter hasta el cierre, conectando tareas, riesgos, decisiones, documentos, costos, materiales, procesos y comunicaciones.

| Comparación | Diferenciación |
| --- | --- |
| Herramientas tradicionales | Tu plataforma propuesta |
| Manejan tareas, tableros y fechas. | Maneja el ciclo completo del proyecto, control ejecutivo, presupuesto, riesgos, cambios, comunicación, documentos e inventario.Mejora de Procesos |
| La comunicación queda fuera del contexto del proyecto. | Emails, reuniones, mensajes, decisiones y documentos quedan atados a proyectos, tareas, riesgos, issues y cambios. |
| Poca relación con ERP, inventario o materiales. | Capa de integración para budget, costos reales, órdenes de compra, materiales, proveedores y stock. |
| Son horizontales y genéricas. | Está diseñada para Project Managers, PMO, operaciones, construcción, instalaciones, tecnología y equipos con control real de proyectos. |

# 2. Principios de diseño del producto

| Principio | Descripción |
| --- | --- |
| Input -> Analysis -> Visualization -> Recommendation | Cada formulario debe alimentar un dashboard, una visualización, un reporte, una alerta o una recomendación de AI. |
| Trazabilidad completa | Cada dato importante debe poder rastrearse hasta su fuente: email, reunión, documento, mensaje, decisión, cambio o registro manual. |
| Metodología guiada | La app debe guiar al usuario por las fases de Project Management: Initiation, Planning, Execution, Monitoring & Controlling, Closing. |
| PMO desde el inicio | La app debe manejar múltiples proyectos, no solo proyectos individuales. |
| Comunicación como control | La comunicación debe convertirse en evidencia: quién dijo qué, cuándo, por qué canal, con qué impacto y qué acción produjo. |
| Documentos vivos | Los documentos no son archivos sueltos: deben tener versión, dueño, estado, relación con cambios y aprobación. |
| Procesos mejorables | Cada proyecto debe permitir detectar cuellos de botella y mejorar procesos usando BPM. |
| ERP-ready | La app debe poder alimentarse de sistemas externos mediante imports, APIs, conectores, webhooks y sincronizaciones programadas. |
| AI con contexto | La AI no debe ser un chatbot aislado; debe interpretar datos reales del proyecto para recomendar acciones. |

# 3. Arquitectura funcional general

La plataforma se debe organizar en capas que se conectan entre sí. La capa superior es PMO/Portfolio; debajo están los proyectos; dentro de cada proyecto viven tareas, riesgos, cambios, comunicaciones, documentos, presupuesto, procesos y materiales. La capa de integración conecta la app con ERP, email, calendario, Slack, Teams, Google Drive, SharePoint u otras fuentes externas.

| Capa | Responsabilidad |
| --- | --- |
| PMO / Portfolio | Vista ejecutiva de múltiples proyectos, priorización, salud general, presupuesto consolidado, riesgos cross-project y capacidad del equipo. |
| Project Lifecycle | Gestión por fases: inicio, planificación, ejecución, monitoreo/control y cierre. |
| Control Modules | Tareas, schedule, budget, riesgos, issues, cambios, documentos y comunicaciones. |
| Operational Modules | BPM, materiales, inventario, proveedores, procurement y procesos internos. |
| Integration Layer | ERP, email, calendario, Slack, Teams, Drive, SharePoint, CSV/Excel, APIs, webhooks. |
| AI Super PM | Análisis, generación, recomendaciones, alertas, reportes, predicción de riesgos y mejora de procesos. |

| Nivel 1 | Nivel 2 | Nivel 3 | Nivel 4 |
| --- | --- | --- | --- |
| Portfolio / PMO | Projects | Dashboards | Reports |
| Projects | Lifecycle | Tasks | Schedule |
| Control | Budget | Risks | Issues / Changes |
| Evidence | Communication | Documents | Decisions |
| Operations | BPM | Materials | ERP Connectors |
| Intelligence | AI Super PM | Alerts | Recommendations |

# 4. PMO / Portfolio Management

Objetivo: Permitir a una organización controlar múltiples proyectos al mismo tiempo, entendiendo salud, prioridad, costo, riesgo, capacidad, avance y dependencias entre proyectos.

## Preguntas que debe responder

- ¿Cuáles proyectos están en verde, amarillo o rojo?

- ¿Qué proyectos están atrasados o sobre presupuesto?

- ¿Dónde están los riesgos más críticos del portafolio?

- ¿Qué recursos están sobrecargados?

- ¿Qué proyectos deben priorizarse o pausarse?

- ¿Qué proyectos dependen de otros?

## Componentes funcionales

- Portfolio dashboard

- Project health scoring

- Project prioritization

- Cross-project risk view

- Cross-project budget view

- Resource capacity by project

- Executive roadmap

- Portfolio status report

- Multi-project dependencies

- Portfolio governance board

| Área | Detalle |
| --- | --- |
| Entradas principales | Projects Tasks Budgets Risks Issues Resources Milestones Change requests |
| Salidas del módulo | Portfolio health report Executive dashboard Prioritized project list Resource overload alerts Cross-project risk register |
| Visualizaciones | Portfolio heatmap Bubble chart: impact/cost/risk Roadmap timeline Budget variance by project Risk heatmap by project Resource capacity chart |
| Automatización / AI | Explain why a project is at risk Recommend which project needs intervention first Summarize portfolio status for executives Detect resource conflicts across projects |
| Conexiones con otros módulos | Projects Budget Risk Resources Reports AI Super PM |
| Alcance recomendado para MVP | List of projects Health score Basic portfolio dashboard Budget and risk summary by project Executive status summary |

## Futuro / Versión avanzada

- Advanced portfolio optimization

- Scenario planning

- What-if analysis

- Program management

- Project scoring model

# 5. Project Charter / Initiation

Objetivo: Crear una base formal para cada proyecto antes de comenzar la planificación detallada. Este módulo debe convertir la idea inicial en un proyecto aprobado y trazable.

## Preguntas que debe responder

- ¿Cuál problema resuelve el proyecto?

- ¿Cuál es el business case?

- ¿Cuáles son los objetivos?

- ¿Qué está dentro y fuera del alcance?

- ¿Cuáles son los entregables principales?

- ¿Quién aprueba el proyecto?

- ¿Cómo se medirá el éxito?

## Componentes funcionales

- Project charter wizard

- Business case

- Goals and objectives

- Scope and exclusions

- High-level deliverables

- Assumptions and constraints

- Success criteria

- Initial stakeholder list

- High-level budget

- High-level timeline

- Initial risks

- Approval workflow

| Área | Detalle |
| --- | --- |
| Entradas principales | Project request Sponsor input Business need Initial budget Stakeholder input Strategic goals |
| Salidas del módulo | Approved project charter Initial scope baseline Initial stakeholder register Initial risk list Approval record |
| Visualizaciones | Charter canvas Scope map Benefits vs cost chart Approval status tracker High-level milestone timeline |
| Automatización / AI | Generate draft charter Convert business need into objectives Suggest deliverables Detect missing scope elements Suggest initial risks |
| Conexiones con otros módulos | Stakeholders Budget Risks Schedule Documents Change Control |
| Alcance recomendado para MVP | Project creation Charter wizard Sponsor approval status Basic business case Scope/in-scope/out-of-scope fields |

## Futuro / Versión avanzada

- Automated charter generation from meeting notes or email

- Strategic alignment scoring

- Executive approval routing

# 6. Stakeholder Management

Objetivo: Identificar, clasificar y gestionar a todas las personas o grupos que afectan o son afectados por el proyecto.

## Preguntas que debe responder

- ¿Quiénes son los stakeholders?

- ¿Quién debe aprobar?

- ¿Quién debe ser consultado?

- ¿Quién solo necesita estar informado?

- ¿Cuál es su nivel de influencia e interés?

- ¿Qué canal y nivel de detalle prefiere cada uno?

- ¿Qué barreras de comunicación existen?

## Componentes funcionales

- Stakeholder register

- Power/interest matrix

- RACI chart

- Stakeholder communication profile

- Influence/interest scoring

- Engagement strategy

- Preferred channel

- Time zone and language preferences

- Backup contact

- Stakeholder change history

| Área | Detalle |
| --- | --- |
| Entradas principales | Project charter Team structure Client contacts Vendors Sponsors RACI definitions |
| Salidas del módulo | Stakeholder map RACI matrix Communication profiles Engagement plan Stakeholder risk indicators |
| Visualizaciones | Power/interest grid RACI table Communication coverage heatmap Stakeholder engagement dashboard |
| Automatización / AI | Suggest missing stakeholders Recommend communication frequency Detect under-communicated stakeholders Draft stakeholder-specific updates |
| Conexiones con otros módulos | Communication Plan Change Control Decision Log Reports Security |
| Alcance recomendado para MVP | Stakeholder register Power/interest matrix RACI roles Preferred channel and frequency |

## Futuro / Versión avanzada

- Stakeholder sentiment tracking

- AI-based engagement risk scoring

- Stakeholder influence network map

# 7. Communication Plan Management

Objetivo: Planificar y controlar qué se comunica, a quién, cuándo, por qué canal, con qué propósito, con qué nivel de detalle, dónde queda guardado y qué respuesta se espera.

## Preguntas que debe responder

- ¿Qué necesita ser comunicado?

- ¿Quién debe comunicar?

- ¿Cuándo y con qué frecuencia?

- ¿Por qué y cómo se comunica?

- ¿Dónde se guarda la información?

- ¿Requiere respuesta o aprobación?

- ¿Qué barreras pueden afectar la comunicación?

- ¿Se está sobre-comunicando o sub-comunicando?

## Componentes funcionales

- Communication plan wizard

- Stakeholder communication profiles

- Communication matrix

- Frequency and channel rules

- Communication goals

- Communication barriers

- Notes and special instructions

- Priority flags

- Access rules

- Communication test checklist

- Feedback loop

- Over/under-sharing detection

- Change communication plan

- Document links

| Área | Detalle |
| --- | --- |
| Entradas principales | Stakeholder map RACI chart Project phase Communication needs Preferred channels Language/time zone Document links Change requests |
| Salidas del módulo | Communication plan Communication schedule Communication reminders Feedback records Communication effectiveness score Communication dashboard |
| Visualizaciones | Communication matrix Communication timeline Coverage heatmap Feedback dashboard Upcoming/overdue communications panel |
| Automatización / AI | Recommend channel and detail level Generate status messages Detect missing stakeholders Summarize feedback Flag unanswered approvals Suggest communication improvements |
| Conexiones con otros módulos | Stakeholders Meetings Documents Change Control Decision Log Reports AI |
| Alcance recomendado para MVP | Manual communication plan Basic communication matrix Stakeholder preferences Feedback and notes Upcoming communications dashboard |

## Futuro / Versión avanzada

- Automated email/calendar scheduling

- AI stakeholder-specific messaging

- Sentiment analysis

- Communication effectiveness analytics

## 7.1 Flujo recomendado del Communication Plan

- Identify: validar stakeholders, RACI, audiencia, necesidades por fase y barreras.

- Document: registrar tipo de comunicación, destinatarios, frecuencia, canal, objetivo, links, notas y responsables.

- Develop: definir contenido, nivel de detalle, formato, documentos asociados, permisos y pruebas necesarias.

- Execute: enviar, registrar o vincular la comunicación al proyecto, tarea, riesgo, cambio o documento correspondiente.

- Check in: medir respuesta, feedback, claridad, cobertura y efectividad.

- Improve: ajustar frecuencia, canal, audiencia, nivel de detalle o reglas del plan.

| Tipo | Destinatarios | Frecuencia | Método | Objetivo | Recurso / Nota |
| --- | --- | --- | --- | --- | --- |
| Project Newsletter | Key Stakeholders | Monthly | Email | Status overview | Link al reporte y PDF |
| Daily Stand-up | Core Team | Daily | Teams / in-person | Progress, blockers, next steps | Notas y action items |
| Sprint Planning & Demo | Core Team + stakeholders | Bi-weekly | Video conference | Backlog grooming, demo, feedback | Planning tracker |
| Release Planning | Core Team | Every 6 weeks | Video / meeting | Launch preparation | Confirm attendance |
| Retrospective | Core Team + stakeholders | Every 6 weeks | Presentation / meeting | Lessons learned and celebration | Retro doc |

# 8. Communication Intelligence Hub

Objetivo: Centralizar emails, reuniones, mensajes, decisiones y action items para que cada comunicación quede vinculada a proyectos, tareas, riesgos, issues, cambios, documentos, materiales, proveedores o stakeholders.

## Preguntas que debe responder

- ¿Dónde se dijo eso?

- ¿Quién aprobó?

- ¿Cuándo se tomó la decisión?

- ¿Qué conversación originó el cambio?

- ¿Qué tarea o riesgo está afectado por este email?

- ¿Qué action items salieron de la reunión?

- ¿Qué evidencia soporta una decisión?

## Componentes funcionales

- Communication inbox

- Project communication timeline

- Email/thread linking

- Meeting management

- Slack/Teams message linking

- Decision extraction

- Action item extraction

- Communication traceability matrix

- Communication evidence map

- AI communication insights

| Área | Detalle |
| --- | --- |
| Entradas principales | Gmail/Outlook emails Calendar events Meeting notes Slack/Teams messages Manual notes Documents Stakeholder replies |
| Salidas del módulo | Linked communication items Action items Decision log entries Risks/issues/change requests created from communications Meeting minutes |
| Visualizaciones | Communication timeline Traceability matrix Decision timeline Action item board Evidence map |
| Automatización / AI | Extract decisions, risks, issues and actions Suggest links to project objects Generate meeting minutes Draft stakeholder updates Detect communication gaps |
| Conexiones con otros módulos | Communication Plan Tasks Risks Issues Change Control Documents Stakeholders |
| Alcance recomendado para MVP | Manual communication log Meeting notes Decision log Action items Basic email linking by copy/paste or upload |

## Futuro / Versión avanzada

- Gmail/Outlook OAuth integration

- Slack/Teams integration

- Automatic classification

- Thread summarization

- AI response drafting

# 9. Document Control

Objetivo: Organizar, controlar y versionar todos los documentos del proyecto, asegurando que el equipo use siempre la versión correcta y que cada documento esté relacionado con la fase, decisión, cambio o evidencia correspondiente.

## Preguntas que debe responder

- ¿Dónde están los documentos del proyecto?

- ¿Cuál es la versión aprobada?

- ¿Quién es el dueño del documento?

- ¿Qué documento fue actualizado por un cambio?

- ¿Qué documentos requieren aprobación?

- ¿Quién tiene acceso?

- ¿Qué evidencia soporta este documento?

## Componentes funcionales

- Project document repository

- Document folder structure by phase

- Document type classification

- Version control

- Approval status

- Access level

- Document owner

- Related object linking

- Document review dates

- Superseded/archived versions

- Document audit trail

| Área | Detalle |
| --- | --- |
| Entradas principales | Uploaded files Google Drive/SharePoint links Email attachments Generated reports Change request documents Meeting minutes |
| Salidas del módulo | Organized document library Approved version tracking Document status dashboard Document-change relationships Access records |
| Visualizaciones | Document tree by phase Approval workflow view Version timeline Documents pending review panel |
| Automatización / AI | Detect outdated document versions Summarize document changes Suggest affected documents after change request Generate document descriptions |
| Conexiones con otros módulos | Communication Plan Change Control Decision Log Reports Security Lifecycle Phases |
| Alcance recomendado para MVP | Basic repository Document type/status/version fields Manual upload/link Current approved version marker |

## Futuro / Versión avanzada

- Google Drive/SharePoint sync

- Automated version comparison

- Document approval workflows

- AI document summaries

## 9.1 Estructura recomendada de documentos por proyecto

| Carpeta / Fase | Documentos |
| --- | --- |
| 01 Initiation | Project Charter, Business Case, Stakeholder Register |
| 02 Planning | WBS, Schedule, Budget Baseline, Risk Management Plan, Communication Plan, Procurement Plan |
| 03 Execution | Meeting Minutes, Status Reports, Vendor Updates, Work Evidence |
| 04 Monitoring & Controlling | Risk Register, Issue Log, Change Requests, Budget Reports, Performance Reports |
| 05 Closing | Lessons Learned, Final Report, Sign-offs, Closure Checklist |

# 10. Change Control

Objetivo: Controlar todo cambio de alcance, cronograma, presupuesto, calidad, riesgo, materiales o procesos, desde su origen hasta su aprobación, implementación, comunicación y cierre.

## Preguntas que debe responder

- ¿Qué cambió?

- ¿Quién pidió el cambio?

- ¿Por qué se necesita?

- ¿Cuál es el impacto en scope, schedule, budget, risk y materiales?

- ¿Quién aprueba?

- ¿Qué documento debe actualizarse?

- ¿Cómo se comunica el cambio?

- ¿Dónde está la evidencia?

## Componentes funcionales

- Change request log

- Change request workflow

- Impact analysis

- Approval board

- Decision evidence

- Change communication plan

- Affected documents

- Affected tasks and milestones

- Budget impact

- Risk impact

- Implementation tracking

- Change closure

| Área | Detalle |
| --- | --- |
| Entradas principales | Email/reunion/message/manual request Tasks Budget baseline Schedule baseline Risk register Material plan Documents |
| Salidas del módulo | Approved/rejected/deferred changes Updated baselines Change impact report Communication actions Document updates |
| Visualizaciones | Change control board Impact chart by scope/schedule/budget Change timeline Approval workflow view |
| Automatización / AI | Classify change type Estimate affected areas Generate impact analysis draft Suggest stakeholders to notify Draft approval email |
| Conexiones con otros módulos | Communication Hub Document Control Budget Schedule Risks Materials Decision Log |
| Alcance recomendado para MVP | Change request form Status workflow Impact fields Approval status Link to evidence and documents |

## Futuro / Versión avanzada

- Automated impact analysis

- Formal approval routing

- Baseline comparison

- Change trend analytics

# 11. Task & Schedule Management

Objetivo: Planificar, ejecutar y controlar el trabajo del proyecto con tareas, milestones, dependencias, fechas, responsables, entregables y estado real.

## Preguntas que debe responder

- ¿Qué hay que hacer?

- ¿Quién es responsable?

- ¿Cuándo debe completarse?

- ¿Qué depende de qué?

- ¿Qué está bloqueado?

- ¿Qué está en la ruta crítica?

- ¿Qué milestone está en riesgo?

- ¿Qué tareas están relacionadas con documentos, riesgos, issues o materiales?

## Componentes funcionales

- Task board

- Milestones

- Deliverables

- Dependencies

- WBS tree

- Gantt chart

- Critical path

- Calendar view

- Task comments

- Task evidence

- Task status workflow

- Resource assignment

- Task-to-material link

- Task-to-budget link

| Área | Detalle |
| --- | --- |
| Entradas principales | Project charter Deliverables WBS Team members Dependencies Material requirements Change requests |
| Salidas del módulo | Project schedule Task status Milestone status Critical path Blocked tasks Progress by deliverable |
| Visualizaciones | Kanban board Gantt chart WBS tree Critical path diagram Calendar Milestone timeline |
| Automatización / AI | Generate tasks from deliverables Suggest dependencies Identify schedule risks Recommend task reassignment Summarize blockers |
| Conexiones con otros módulos | Budget Risks Issues Materials Communication Reports BPM |
| Alcance recomendado para MVP | Tasks, statuses, owners, due dates, milestones, dependencies, basic Gantt/Kanban |

## Futuro / Versión avanzada

- Advanced scheduling

- Resource leveling

- Critical chain

- Automated dependency detection

- Predictive schedule forecasting

# 12. Budget Management

Objetivo: Controlar el presupuesto planificado, costo real, forecast, variaciones, burn rate, impacto financiero de cambios y costo por tareas, materiales, proveedores o recursos.

## Preguntas que debe responder

- ¿Cuál es el presupuesto aprobado?

- ¿Cuánto se ha gastado?

- ¿Cuál es el forecast al cierre?

- ¿Dónde está la variación?

- ¿Qué cambios impactaron el budget?

- ¿Qué materiales o proveedores consumen más costo?

- ¿Qué tareas están sobre presupuesto?

## Componentes funcionales

- Budget baseline

- Budget categories

- Planned cost

- Actual cost

- Forecast cost

- Cost variance

- Burn rate

- Budget by task

- Budget by milestone

- Labor/material/vendor cost

- Contingency reserve

- Management reserve

- Change financial impact

- EVM indicators

| Área | Detalle |
| --- | --- |
| Entradas principales | Approved budget ERP actuals Purchase orders Timesheets/labor cost Material consumption Change requests |
| Salidas del módulo | Budget dashboard Variance alerts Forecast at completion Cost performance summary Budget impact analysis |
| Visualizaciones | Planned vs actual chart S-curve Budget burn chart Cost variance by category EVM dashboard |
| Automatización / AI | Explain budget variance Forecast overrun risk Suggest corrective actions Generate budget status summary Detect unusual cost patterns |
| Conexiones con otros módulos | ERP Integration Materials Tasks Change Control Reports PMO |
| Alcance recomendado para MVP | Budget baseline, actual cost manual entry/import, variance dashboard, budget by category |

## Futuro / Versión avanzada

- Full EVM, ERP automated actuals, cost forecasting, scenario analysis, approval thresholds

# 13. Risk Management

Objetivo: Identificar, analizar, priorizar, comunicar y controlar riesgos del proyecto, conectándolos con tareas, materiales, presupuesto, proveedores, procesos y cambios.

## Preguntas que debe responder

- ¿Qué puede afectar el proyecto?

- ¿Cuál es la probabilidad e impacto?

- ¿Quién es el dueño del riesgo?

- ¿Cuál es el trigger?

- ¿Cuál es el plan de mitigación?

- ¿Qué tarea, material o proveedor está afectado?

- ¿Qué riesgos se convirtieron en issues?

## Componentes funcionales

- Risk register

- Risk categories

- Probability/impact scoring

- Risk response strategy

- Mitigation plan

- Contingency plan

- Risk owner

- Trigger

- Cost/schedule impact

- Risk status

- Risk review cadence

- Risk-to-issue conversion

| Área | Detalle |
| --- | --- |
| Entradas principales | Project plan Tasks Supplier info Material availability Budget variance Stakeholder feedback AI insights |
| Salidas del módulo | Risk register Risk heatmap Top risks Mitigation actions Risk exposure trend |
| Visualizaciones | Risk matrix Risk burndown Risk exposure trend Top 10 risks Risk by category/owner |
| Automatización / AI | Suggest risks from project data Generate mitigation plans Detect emerging risks Explain risk exposure Recommend escalation |
| Conexiones con otros módulos | Tasks Issues Change Control Materials Budget Communication Reports |
| Alcance recomendado para MVP | Risk register with probability, impact, score, owner, mitigation, status and linked tasks |

## Futuro / Versión avanzada

- Predictive risk scoring, automatic risk detection from communications, Monte Carlo-style schedule/cost risk analysis

# 14. Issue Management

Objetivo: Registrar, priorizar y resolver problemas reales que ya están afectando el proyecto, diferenciándolos claramente de los riesgos futuros.

## Preguntas que debe responder

- ¿Qué problema está ocurriendo?

- ¿Cuándo se detectó?

- ¿Quién es responsable de resolverlo?

- ¿Cuál es la prioridad?

- ¿Qué tarea, milestone o stakeholder está afectado?

- ¿Qué riesgo se materializó?

- ¿Cuál es el plan de resolución?

## Componentes funcionales

- Issue log

- Issue priority

- Issue owner

- Resolution plan

- Due date

- Escalation path

- Root cause

- Related risk

- Related task

- Related change request

- Issue aging

- Issue closure validation

| Área | Detalle |
| --- | --- |
| Entradas principales | Team reports Emails/messages Risk triggers Task blockers Supplier updates Material shortages |
| Salidas del módulo | Open/closed issues Resolution actions Escalations Lessons learned inputs Issue performance metrics |
| Visualizaciones | Issue board Issue aging chart Issue by owner Blocker dashboard Root cause Pareto |
| Automatización / AI | Detect issue from communication Suggest root cause Recommend resolution actions Draft escalation message |
| Conexiones con otros módulos | Risk Management Tasks Communication Hub Change Control BPM Reports |
| Alcance recomendado para MVP | Issue log with priority, owner, status, resolution plan and linked task/risk |

## Futuro / Versión avanzada

- AI root cause analysis, automatic escalation, recurring issue pattern detection

# 15. BPM / Process Improvement

Objetivo: Permitir que cada proyecto no solo se ejecute, sino que también mejore los procesos internos asociados al trabajo, detectando cuellos de botella, retrasos, retrabajo y oportunidades de mejora.

## Preguntas que debe responder

- ¿Qué proceso soporta esta parte del proyecto?

- ¿Cuáles son los pasos del proceso?

- ¿Quién es responsable de cada paso?

- ¿Cuál es el SLA esperado?

- ¿Dónde están los cuellos de botella?

- ¿Qué paso genera retrabajo?

- ¿Qué mejora se puede implementar?

## Componentes funcionales

- Process map

- Process steps

- Process owners

- SLA per step

- Actual cycle time

- Bottleneck detection

- Approval workflow

- Rework tracking

- Process cost

- Process defects

- Improvement backlog

- Process improvement recommendations

| Área | Detalle |
| --- | --- |
| Entradas principales | Project workflows Task timestamps Approvals Issue data Material request flow Communication delays |
| Salidas del módulo | Process maps Bottleneck alerts Improvement actions Cycle time metrics Process performance report |
| Visualizaciones | BPMN-style diagram Swimlane diagram Cycle time chart Bottleneck chart Rework percentage Process efficiency score |
| Automatización / AI | Detect bottlenecks Suggest process improvement Analyze delay causes Recommend approval automation Summarize process performance |
| Conexiones con otros módulos | Tasks Issues Communication Change Control Materials Reports AI |
| Alcance recomendado para MVP | Create process, define steps/owners/SLA, track status and cycle time, basic process map |

## Futuro / Versión avanzada

- Advanced BPMN editor, process simulation, automated workflow execution, continuous improvement scoring

# 16. Materials & Inventory Management

Objetivo: Conectar los materiales, inventario, proveedores y órdenes de compra con las tareas y milestones del proyecto para evitar retrasos por falta de materiales o mala visibilidad de stock.

## Preguntas que debe responder

- ¿Qué materiales requiere cada tarea?

- ¿Están disponibles?

- ¿Dónde están ubicados?

- ¿Cuándo se necesitan?

- ¿Qué proveedor los entrega?

- ¿Qué material está reservado para qué proyecto?

- ¿Qué shortage puede retrasar un milestone?

- ¿Cuál es el costo de materiales por proyecto?

## Componentes funcionales

- Material catalog

- Project material requirements

- Material by task/milestone

- Inventory locations

- Stock availability

- Material reservation

- Material consumption

- Purchase requests

- Purchase orders

- Supplier tracking

- Delivery dates

- Shortage alerts

- Material cost by project

| Área | Detalle |
| --- | --- |
| Entradas principales | Material catalog Inventory data ERP stock Purchase orders Supplier delivery dates Task requirements |
| Salidas del módulo | Material availability report Shortage alerts Material consumption records Procurement requests Material cost summary |
| Visualizaciones | Materials required vs available Material shortage dashboard Consumption chart Supplier delivery performance Forecast demand chart |
| Automatización / AI | Predict material shortage Recommend reorder Identify supplier delay risk Connect material issue to schedule impact |
| Conexiones con otros módulos | Tasks Budget ERP Integration Risk Issue Management Procurement Reports |
| Alcance recomendado para MVP | Material catalog, task-material link, manual stock, shortage alerts, supplier/delivery fields |

## Futuro / Versión avanzada

- ERP inventory sync, warehouse management, barcode scanning, procurement workflows, demand forecasting

# 17. ERP Integration Layer

Objetivo: Crear una capa flexible para que la plataforma pueda alimentarse de sistemas externos sin depender de un solo ERP.

## Preguntas que debe responder

- ¿Qué datos vendrán del ERP?

- ¿Cómo se importan costos reales?

- ¿Cómo se actualiza inventario?

- ¿Cómo se relacionan órdenes de compra con proyectos?

- ¿Cómo se sincronizan vendors, invoices, materiales y cost centers?

- ¿Qué pasa si una empresa usa SAP, Oracle, Dynamics, Odoo o un ERP custom?

## Componentes funcionales

- Connector framework

- Manual entry

- CSV/Excel import

- API connectors

- Database connectors

- Webhooks

- Scheduled sync

- Field mapping

- Sync logs

- Error handling

- Data validation

- ERP object mapping

| Área | Detalle |
| --- | --- |
| Entradas principales | ERP data CSV/Excel files APIs Database tables Webhooks Manual imports |
| Salidas del módulo | Imported actual costs Inventory updates Vendor lists Purchase orders Invoices Cost centers Sync status |
| Visualizaciones | Sync health dashboard Import validation report ERP mapping view Data freshness indicator |
| Automatización / AI | Suggest field mapping Detect anomalies in imports Summarize sync errors Recommend missing fields |
| Conexiones con otros módulos | Budget Inventory Materials Vendors Reports Security AI |
| Alcance recomendado para MVP | CSV/Excel import, generic API connector structure, sync logs, manual mapping interface |

## Futuro / Versión avanzada

- Native SAP/Oracle/Dynamics/NetSuite/QuickBooks/Odoo connectors, webhooks, scheduled jobs, data warehouse layer

# 18. Reports & Dashboards

Objetivo: Convertir todos los datos del proyecto en visibilidad ejecutiva, reportes operativos, alertas y análisis de performance.

## Preguntas que debe responder

- ¿Cómo está el proyecto?

- ¿Qué está atrasado?

- ¿Qué está sobre presupuesto?

- ¿Qué riesgos son críticos?

- ¿Qué cambios están pendientes?

- ¿Qué documentos faltan?

- ¿Qué stakeholders no han sido actualizados?

- ¿Qué acciones recomienda la app?

## Componentes funcionales

- Project dashboard

- Portfolio dashboard

- Executive status report

- Weekly status report

- Risk dashboard

- Budget dashboard

- Schedule dashboard

- Communication dashboard

- Change dashboard

- Document dashboard

- Materials dashboard

- BPM dashboard

- Closing report

| Área | Detalle |
| --- | --- |
| Entradas principales | All module data: tasks, schedule, budget, risks, issues, changes, docs, communications, materials, processes |
| Salidas del módulo | Dashboards, PDF reports, executive summaries, alerts, status updates, exportable data |
| Visualizaciones | Health cards Traffic lights S-curves Risk heatmaps Gantt Kanban Budget charts Timeline, heatmaps, trend charts |
| Automatización / AI | Generate narrative reports Explain red/yellow status Recommend corrective actions Create stakeholder-specific reports |
| Conexiones con otros módulos | All modules AI Super PM Communication Plan PMO |
| Alcance recomendado para MVP | Project dashboard, weekly status report, risk/budget/task dashboards, export to PDF |

## Futuro / Versión avanzada

- Custom dashboard builder, KPI library, cross-project analytics, predictive dashboards, BI integration

# 19. AI Super Project Manager

Objetivo: Actuar como un asistente experto conectado al contexto real del proyecto para generar, analizar, recomendar y alertar.

## Preguntas que debe responder

- ¿Qué debo hacer ahora?

- ¿Por qué el proyecto está en riesgo?

- ¿Qué riesgos faltan?

- ¿Qué tareas debo crear?

- ¿Qué comunicación debo enviar?

- ¿Qué cambio impacta budget o schedule?

- ¿Qué documento está desactualizado?

- ¿Dónde está el cuello de botella?

## Componentes funcionales

- Project charter assistant

- Task generation assistant

- Risk identification assistant

- Status report generator

- Communication assistant

- Change impact assistant

- Budget variance analyst

- Process improvement advisor

- Material shortage predictor

- Meeting minutes generator

- Lessons learned generator

- Executive summary generator

| Área | Detalle |
| --- | --- |
| Entradas principales | Project data, communications, documents, tasks, risks, issues, budget, materials, ERP data, meeting notes |
| Salidas del módulo | Recommendations, generated documents, draft communications, alerts, summaries, risks, tasks, reports |
| Visualizaciones | AI insights panel Recommendation queue Project health explanation Risk/action suggestions Narrative summary cards |
| Automatización / AI | All listed functionality is AI-driven. The assistant must always cite or link the project data source/evidence when making recommendations. |
| Conexiones con otros módulos | All modules |
| Alcance recomendado para MVP | Status report generator, risk suggestions, task suggestions, meeting minutes, communication drafting |

## Futuro / Versión avanzada

- Predictive PMO assistant, autonomous project diagnostics, scenario simulation, natural language project query engine

# 20. Security, Roles & Permissions

Objetivo: Proteger información sensible del proyecto, controlar acceso por organización, proyecto, rol y tipo de dato, y mantener auditoría de acciones críticas.

## Preguntas que debe responder

- ¿Quién puede ver qué?

- ¿Quién puede editar?

- ¿Quién puede aprobar cambios?

- ¿Quién puede ver comunicaciones sensibles?

- ¿Quién puede acceder a documentos financieros?

- ¿Quién puede conectar un ERP?

- ¿Qué acciones deben auditarse?

## Componentes funcionales

- Organizations

- Users

- Teams

- Roles

- Permissions

- Project-level access

- Document-level access

- Communication access rules

- Financial data restrictions

- ERP connector permissions

- Audit log

- OAuth integrations

- Data retention rules

| Área | Detalle |
| --- | --- |
| Entradas principales | Users, teams, roles, project assignments, document sensitivity, integration permissions |
| Salidas del módulo | Access decisions, audit records, restricted views, permission matrix, security alerts |
| Visualizaciones | Role permission matrix Audit trail timeline Access review dashboard |
| Automatización / AI | Detect sensitive data exposure risk Recommend access restrictions Summarize audit events |
| Conexiones con otros módulos | All modules, especially Communication, Documents, ERP, Budget |
| Alcance recomendado para MVP | Basic RBAC: admin, PM, team member, stakeholder, client/vendor read-only; project-level permissions |

## Futuro / Versión avanzada

- Attribute-based permissions, SSO/SAML, enterprise audit, field-level security, data residency controls

# 21. Database Structure

La base de datos debe diseñarse alrededor de una organización, múltiples proyectos y objetos trazables. La regla principal es que casi todo debe poder conectarse con proyectos, tareas, riesgos, issues, cambios, documentos, comunicaciones y decisiones.

| Dominio | Tablas sugeridas |
| --- | --- |
| Core | organizations, users, teams, team_members, roles, permissions, audit_logs |
| Portfolio / PMO | project_portfolios, portfolio_projects, project_priorities, project_health_scores |
| Projects | projects, project_charters, project_goals, project_deliverables, project_phases, project_approvals |
| Stakeholders | stakeholders, stakeholder_profiles, raci_matrix, stakeholder_engagement_logs |
| Communication | communication_plans, communication_plan_items, communication_recipients, communication_items, communication_threads, communication_links, communication_feedback |
| Meetings / Decisions | meetings, meeting_attendees, meeting_notes, meeting_decisions, action_items, decision_log |
| Documents | documents, document_versions, document_links, document_approvals, document_access_rules |
| Change Control | change_requests, change_impact_analysis, change_approvals, change_communications, change_documents |
| Tasks / Schedule | project_tasks, task_dependencies, milestones, deliverables, task_comments, task_evidence |
| Budget | budgets, budget_categories, budget_baselines, budget_actuals, cost_forecasts, budget_variances |
| Risks / Issues | risks, risk_mitigations, risk_triggers, issues, issue_actions, issue_escalations |
| BPM | processes, process_steps, process_metrics, process_improvements, process_instances |
| Materials / Inventory | materials, project_materials, inventory_locations, inventory_transactions, suppliers, purchase_requests, purchase_orders |
| ERP | erp_connections, erp_mappings, erp_sync_logs, erp_import_batches, erp_import_errors |
| Reports / AI | status_reports, dashboard_configs, ai_recommendations, ai_insights, ai_generated_outputs |

## 21.1 Modelo de trazabilidad universal

Para evitar relaciones rígidas y permitir que un email, documento, decisión o cambio se conecte con varios objetos, se recomienda crear tablas de linking genéricas o específicas por dominio.

| Tabla | Campos clave |
| --- | --- |
| communication_links | communication_item_id, project_id, task_id, risk_id, issue_id, change_request_id, document_id, stakeholder_id, material_id, link_type, confidence_score |
| document_links | document_id, project_id, task_id, risk_id, issue_id, change_request_id, meeting_id, decision_id, material_id |
| decision_links | decision_id, project_id, task_id, risk_id, issue_id, change_request_id, budget_id, document_id |
| ai_recommendation_links | ai_recommendation_id, project_id, related_object_type, related_object_id, evidence_source_type, evidence_source_id |

# 22. MVP Roadmap

La plataforma es grande. Para reducir riesgo técnico y de producto, se recomienda construir en fases. La primera versión debe demostrar el diferencial: project control profesional con comunicación, riesgos, cambios, documentos, budget y dashboards.

| Fase | Alcance |
| --- | --- |
| MVP 1 - Core Project Control | Organizations, users, projects, project charter, stakeholders, RACI, tasks, milestones, risk register, issue log, basic budget, document repository, communication plan, change requests, dashboard, AI status report. |
| MVP 2 - Communication + Documents + Change Deepening | Communication hub, meeting notes, decision log, action items, document version control, change communication plan, feedback loop, communication coverage heatmap. |
| MVP 3 - BPM / Process Improvement | Processes, process steps, owners, SLA, cycle time, bottleneck detection, process map, improvement actions. |
| MVP 4 - Materials / Inventory | Material catalog, project material requirements, inventory availability, supplier tracking, purchase requests, material shortage alerts. |
| MVP 5 - ERP / Integrations | CSV/Excel imports, connector framework, scheduled sync, actual cost import, inventory import, vendor/purchase order import. |
| MVP 6 - Advanced PMO + AI | Portfolio dashboard, resource capacity, cross-project dependencies, advanced AI analysis, predictive risk/budget/schedule insights. |

# 23. Navegación y UX propuesta

| Área | Pantallas |
| --- | --- |
| Global | Dashboard, Portfolio / PMO, Projects, Reports, AI Super PM, Integrations, Settings |
| Project detail | Overview, Lifecycle, Tasks & Schedule, Budget, Risks, Issues, Changes, Stakeholders, Communication, Documents, BPM, Materials, Reports |
| Communication area | Communication Plan, Communication Hub, Meetings, Decision Log, Action Items, Feedback, Traceability Matrix |
| Control area | Change Control Board, Document Repository, Risk Matrix, Issue Board, Budget Dashboard |
| Operations area | Process Maps, Materials, Inventory, Suppliers, Purchase Requests |

## 23.1 Principios UX

- No mostrar todo al mismo tiempo: usar navegación por fases y tabs por módulo.

- Cada proyecto debe tener un health card visible: scope, schedule, budget, risk, communication, documents.

- Cada objeto debe mostrar sus relaciones: tareas relacionadas, riesgos, documentos, decisiones, comunicaciones y cambios.

- Cada alerta debe explicar causa, evidencia e impacto.

- Cada módulo debe tener vista de lista, vista dashboard y vista detalle.

- La app debe permitir trabajar manualmente primero y automatizar después con integraciones.

# 24. Decisiones pendientes antes del prompt final

Antes de construir el prompt final para Claude/Antigravity, conviene cerrar algunas decisiones de producto. Esto evitará que la AI construya algo demasiado amplio, ambiguo o difícil de mantener.

| Decisión | Opciones / comentario |
| --- | --- |
| Nombre del producto | ProjectOps360, PMOFlow, SuperPM u otro. |
| Cliente objetivo inicial | PMs individuales, PMO, construcción/instalación, tecnología, operaciones, estudiantes de PM, pequeñas empresas. |
| Stack técnico | Supabase/Postgres, React/Next.js, FlutterFlow, Firebase, Node, Python, etc. |
| MVP real | Decidir si MVP 1 incluye solo core project control o también communication/document/change control más fuerte. |
| Integraciones iniciales | Manual/CSV primero, luego Google, luego Microsoft, luego Slack/ERP. |
| Modelo AI | AI como asistente contextual con evidencia, no como chatbot genérico. |
| Nivel de metodología | PMBOK/Coursera-inspired, Agile/Scrum, hybrid, BPM, EVM. |
| Permisos | Definir roles mínimos para lanzamiento: Admin, PM, Team Member, Stakeholder, Client/Vendor. |
| Documentos | Determinar si se almacenan archivos o solo links a Drive/SharePoint en MVP. |
| Comunicación | Determinar si MVP usa log manual primero o conexión directa a Gmail/Outlook desde el inicio. |

# Apéndice A. Checklist de módulos definidos

- PMO / Portfolio Management

- Project Charter e Initiation

- Stakeholder Management

- Communication Plan Management

- Communication Intelligence Hub

- Document Control

- Change Control

- Task & Schedule Management

- Budget Management

- Risk Management

- Issue Management

- BPM / Process Improvement

- Materials & Inventory Management

- ERP Integration Layer

- Reports & Dashboards

- AI Super Project Manager

- Security, Roles & Permissions

- Database Structure

- MVP Roadmap

- Navegación y UX

- Decisiones pendientes antes del prompt final

# Apéndice A - Formatos del Plan de Documentación y Tablas de Plantillas

Fuente: Project-plan.xlsx - Plant Pals Operations & Training Plan

Este apéndice agrega los formatos del spreadsheet que deben estar accesibles desde los módulos de Document Control y Communication Plan de la plataforma. Cada formato debe guardarse como documento administrado del proyecto, versionado, vinculado al módulo correcto y conectado con los registros relacionados del proyecto.

Cómo deben funcionar estos formatos dentro de la plataforma

- Cada plantilla debe tener document type, owner, access level, status, current approved version y project phase relacionado.

- Cada plantilla debe poder vincularse con registros del proyecto como tareas, riesgos, budget items, communication items, decisions y change requests.

- La app debe permitir cargar, generar, exportar, versionar, revisar, aprobar, archivar y referenciar estos formatos en reportes.

- Cuando un change request modifique scope, schedule, budget, communication o risk, la plantilla relacionada debe marcarse para revisión y actualización de versión.

Las tablas siguientes conservan el contenido del workbook Plant Pals como tablas editables de Word para revisión del producto. El grid completo del Gantt se representa aquí mediante la tabla de tareas para mantener legibilidad; la aplicación debe seguir soportando una visualización Gantt completa dentro del módulo Schedule.

## A.1 Matriz de acceso a plantillas

| Formato / Hoja de origen | Módulo de la app | Fase del proyecto | Propósito | Responsable principal | Registros conectados |
| --- | --- | --- | --- | --- | --- |
| Dashboard de documentación / Key Docs | Control de Documentos | Initiation, Planning, Control | Crear un índice estructurado de todos los documentos y recursos principales del proyecto. | Project Manager | Charter, SoW, plan de riesgos, cronograma, presupuesto, plan de comunicación, carpeta compartida, RACI |
| Project Schedule / Gantt | Task & Schedule Management | Planning, Execution, Monitoring & Controlling | Controlar milestones, tareas, responsables, fechas de inicio, fechas de entrega, duración y porcentaje completado. | Project Manager / Task Owners | Tareas, milestones, dependencias, baseline del schedule, reportes de estado |
| Budget | Budget Management | Planning, Monitoring & Controlling | Controlar target budget, actual/final spend, labor, materiales, costos fijos, reserva y variación under/over. | Financial Analyst / Project Manager | Budget baseline, actual costs, materiales, labor, change requests |
| Communication Plan | Communication Plan Management | Planning, Execution, Monitoring & Controlling | Definir recipients, tipo de comunicación, frecuencia, owner, fechas clave, delivery method, goals, resource links y notes. | Project Manager / Communication Owner | Stakeholders, RACI, reuniones, decision log, document links, change communications |

## A.2 Dashboard de documentación del proyecto / Key Docs

Propósito: indexar los documentos principales del proyecto y hacerlos accesibles desde el repositorio de documentos, communication plan, change control y project dashboard.

| Key Docs | Description |
| --- | --- |
| Project charter | An overview of the project, key elements and expectations |
| Statement of work | Identifies the work that is included in the project and the pricing that was quoted initially. |
| Risk management plan | Identifies the potential risks to the project, their likelihood, and how you plan to mitigate them if they become realized. |
| Schedule | Identifies the planned schedule as well as any changes through out the project lifecycle. |
| Budget | Identifies the planned budget as well as any over and under runs. Allows you to estimate the cost at completion. |
| Communication plan | Identifies how often, what type of communication method, and what information your stakeholders needs to know |
| Shared folder | Folder with all relevant documentation |
| RACI chart | Identifies who is responsible, accountable, consulted and informed within the project. |

## A.3 Project Schedule / Gantt Task Table

Metadata del schedule extraída del workbook.

| Title | Plant Pals Operations and Training Plan |
| --- | --- |
| Project Manager | Project Manager |
| Company Name | Office Green |
| Creation Date | 02/15 |

Tabla de tareas extraída de la plantilla de Gantt schedule.

| TASK ID NUMBER | MILESTONES & TASKS | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Establish a plant delivery and logistics plan |  |  |  |  |  |
| 1.1 | Source packaging materials | Fulfillment Director | 3/1 | 3/12 | 10 | 0 |
| 1.2 | Hire delivery drivers | HR Specialist | 3/15 | 3/26 | 10 | 0 |
| 1.3 | Calculate delivery fees | Financial Analyst | 3/29 | 4/9 | 10 | 0 |
| 2 | Select and install supply chain software and equipment |  |  |  |  |  |
| 2.1 | Supervise vendor setup of inventory management and fulfillment software | Inventory manager | 4/12 | 4/14 | 3 | 0 |
| 2.2 | Supervise vendor installation of fulfillment equipment | Fulfillment Director | 4/15 | 4/16 | 2 | 0 |
| 2.3 | Determine internal safety protocols for equipment | Quality Assurance Tester | 4/19 | 4/30 | 10 | 0 |
| 3 | Develop and launch an employee training program |  |  |  |  |  |
| 3.1 | Develop training sessions | HR Specialist | 5/3 | 5/14 | 10 | 0 |
| 3.2 | Train employees to use the software and equipment | Training Manager | 5/17 | 5/28 | 20 | 0 |
| 3.3 | Monitor employee progress and improve training processes | Training Manager | 5/31 | 6/11 | 10 | 0 |

## A.4 Budget Table

Resumen del presupuesto.

| Target Budget | 62000 |
| --- | --- |
| Actual / Final Spend | 0 |
| Under / Over | 62000 |

Detalle del presupuesto por milestone, task, labor, materiales, fixed cost, budget, actual y variación under/over.

|  | LABOR |  |  | MATERIALS |  | FIXED COST | BUDGET | ACTUAL | UNDER/OVER |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| MILESTONES & TASKS | EMPLOYEE | HOURS | RATE | UNITS | $/UNIT(S) |  |  |  |  |
| Milestone 1: Establish a plant delivery and logistics plan |  |  |  |  |  |  |  |  |  |
| Task 1: Purchase delivery trucks | -- |  |  | 2 | 15000 |  | 30000 |  | -30000 |
| Task 2: Source packaging materials | -- |  |  | 1500 | 2 |  | 3000 |  | -3000 |
| Task 3: Pay delivery drivers | Delivery Drivers (2) | 160 | 15 |  |  |  | 2400 |  | -2400 |
|  |  |  |  |  |  | Total | 35400 | 0 |  |
| Milestone 2: Select and install supply chain management software and equipment |  |  |  |  |  |  |  |  |  |
| Task 1: Source vendor (includes set up, installation, and deployment of systems) | -- |  |  |  |  | 15000 | 15000 |  | -15000 |
|  |  |  |  |  |  | Total | 15000 | 0 |  |
| Milestone 3: Develop and launch an employee training program |  |  |  |  |  |  |  |  |  |
| Task 1: Develop training sessions | HR Specialist | 80 | 50 |  |  |  | 4000 |  | -4000 |
| Task 2: Train employees to use the software and equipment | Training Manager | 80 | 25 |  |  |  | 2000 |  | -2000 |
| Task 3: Monitor employee progress and improve training processes | Training Manager | 80 | 25 |  |  |  | 2000 |  | -2000 |
|  |  |  |  |  |  | Total | 8000 | 0 |  |
| Reserve buffer |  |  |  |  |  |  | 3600 |  |  |
| TOTAL |  |  |  |  |  |  | 62000 | 0 |  |

## A.5 Communication Plan Table

Tabla de Communication Plan extraída del plan de comunicación de entrenamiento de empleados de Plant Pals.

| Recipients | Type of Communication | Frequency | Sender/Owner | Key Dates | Delivery Method | Goal | Resource Links | Notes |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Core Team | Planning Meeting | Daily | Project Manager | Every day at 3pm | In Person | Project planning and task updates to make sure the team stays on track | [link to meeting agenda and notes] | If needed, check in with manager about any high-level questions before meetings. |
| Software and Equipment Vendor | Planning Meeting | One time | Core Team: HR Specialist & Training Manager | Half day, Friday before development of the training plan begins; confirm date and time three days in advance | In Person | Go over the training manual in order to create an effective training plan for Office Green's employees | [link to vendor SoW] | This meeting needs to take place before the end of the vendor's SoW. Make sure the HR Specialist & Training Manager check in with fulfillment and inventory team members about the outcome of the meeting. |
| Human Resources | Planning Check-In | Weekly | Core Team: HR Specialist | Also send reminders (via email) the day before each training | In Person | Project planning assistance; provide support during the training session |  | Additional communication on an as-needed basis |
| Facilities | Planning Check-In | Weekly | Core Team: Administrative Coordinator | Tuesdays at 2pm | Phone Call | Reserve rooms, spaces, and equipment needed for employee training | [link to room and equipment reservation form] |  |
| Print Shop | Planning Check-In | Weekly | Core Team: Administrative Coordinator | Thursdays, including the day before the event | Phone Call | Coordinate on the printing and delivery of training manuals for employees | [link to printing order form] |  |
| Office Green employees | Informational Update | Weekly | Core Team: Training Manager | Fridays, including the Friday before training sessions begin | Email (from company address) | Communicate schedules, locations, and other necessary details to trainees | [trainee email list] | Set up automated reminder emails |
| Office Green employees | Training | Daily | Core Team: Training Manager | Each day for ten days, starting at 10am | In Person | Train employees to use the supply chain management software and equipment | [link to training schedule] |  |
| Office Green employees | Survey | One time | Core Team: Training Manager | The first business day after trainings end, with two follow-up reminders | Email (from company address) | Post-training survey | [trainee email list] | Discuss results at next team meeting |
| Your Manager | Status Update | Weekly | Project Manager | Monday afternoons at 2pm | In Person | Update on event planning, ask questions, and get feedback |  | Come prepared with a brief update and specific questions |
| Senior Leaders: Director of Operations and the Director of Product (and CC your manager) | Status Update | One time | Project Manager | Debrief the week after the event | Email (from individual address) | High-level information and general updates | [link to folder with training notes and survey results] |  |

Implicación para el producto

- Estas plantillas deben convertirse en registros administrados, buscables y vinculables, no simplemente archivos estáticos.

- El Plan de Documentación debe exponer estos formatos como plantillas reutilizables de proyecto y permitir adjuntarlas a comunicaciones, reuniones, change requests, riesgos, budget reviews y closing reports.

- La tabla de Communication Plan debe tratarse como un objeto activo de control que genera recordatorios, reuniones, action items, follow-ups y métricas de efectividad de comunicación.