Master Product Document

Intelligent Project Control Platform for PMO, BPM, Budget, Risk, Communication, Documents, Materials and ERP Integration

Concept Review Version - English

| Item | Description |
| --- | --- |
| Concept names | ProjectOps360 / PMOFlow / SuperPM |
| Purpose | Define all functional modules for a professional project control platform that combines project management methodology, PMO governance, BPM, communication, change control, document control, budget, risk, inventory, ERP integrations and AI. |
| Core principle | Every task, communication, document, risk, change, decision, cost and material must be connected and traceable. |
| Current stage | Functional product definition before creating the final development prompt. |

# Table of Contents

1. Product vision and positioning

2. Product design principles

3. General functional architecture

4. PMO / Portfolio Management

5. Project Charter and Initiation

6. Stakeholder Management

7. Communication Plan Management

8. Communication Intelligence Hub

9. Document Control

10. Change Control

11. Task & Schedule Management

12. Budget Management

13. Risk Management

14. Issue Management

15. BPM / Process Improvement

16. Materials & Inventory Management

17. ERP Integration Layer

18. Reports & Dashboards

19. AI Super Project Manager

20. Security, Roles & Permissions

21. Database Structure

22. MVP Roadmap

23. Navigation and UX

24. Pending decisions before the final prompt

# 1. Product vision and positioning

The proposed platform should not compete with Asana, Trello, Monday or ClickUp as a simple task manager. It should be positioned as a professional Project Operating System: a platform to control complete projects with methodology, traceability, budget governance, risk management, communication, document control, process improvement, materials, ERP data and AI recommendations.

The central product promise is:

Control projects like a professional PMO: from charter to closeout, connecting tasks, risks, decisions, documents, costs, materials, processes and communications.

| Comparison | Differentiation |
| --- | --- |
| Traditional tools | Proposed platform |
| Manage tasks, boards and dates. | Manages the full project lifecycle, executive control, budget, risk, change, communication, documents and inventory. |
| Communication is usually outside the project context. | Emails, meetings, messages, decisions and documents are linked to projects, tasks, risks, issues and changes. |
| Limited relationship with ERP, inventory or materials. | Integration layer for budget, actual costs, purchase orders, materials, vendors and stock. |
| Generic and horizontal. | Designed for Project Managers, PMOs, operations, construction, installation, technology and teams that need real project control. |

# 2. Product design principles

| Principle | Description |
| --- | --- |
| Input -> Analysis -> Visualization -> Recommendation | Every form must feed a dashboard, visualization, report, alert or AI recommendation. |
| Complete traceability | Every important data point must be traceable back to its source: email, meeting, document, chat message, decision, change or manual record. |
| Guided methodology | The app must guide users through the project management lifecycle: Initiation, Planning, Execution, Monitoring & Controlling, and Closing. |
| PMO from the beginning | The platform must support multiple projects, not only individual project workspaces. |
| Communication as control | Communication must become evidence: who said what, when, through which channel, with what impact and what action resulted. |
| Living documents | Documents are not loose files; they need versioning, ownership, status, approval and links to changes or decisions. |
| Improve processes, not only tasks | Each project should allow process bottlenecks to be identified and improved using BPM concepts. |
| ERP-ready architecture | The app must be designed to receive data through imports, APIs, connectors, webhooks and scheduled syncs. |
| Context-aware AI | AI should not be isolated. It must interpret real project data and recommend corrective actions. |

# 3. General functional architecture

The platform should be organized in connected layers. The top layer is PMO/Portfolio. Under that are projects. Inside each project live tasks, schedules, risks, changes, communications, documents, budget, processes and materials. The integration layer connects the app with ERP, email, calendar, Slack, Teams, Google Drive, SharePoint and other sources.

| Layer | Responsibility |
| --- | --- |
| PMO / Portfolio | Executive view of multiple projects, prioritization, overall health, consolidated budget, cross-project risks and team capacity. |
| Project Lifecycle | Project management by phase: Initiation, Planning, Execution, Monitoring & Controlling, and Closing. |
| Control Modules | Tasks, schedule, budget, risks, issues, changes, documents and communications. |
| Operational Modules | BPM, materials, inventory, suppliers, procurement and internal processes. |
| Integration Layer | ERP, email, calendar, Slack, Teams, Drive, SharePoint, CSV/Excel, APIs and webhooks. |
| AI Super PM | Analysis, generation, recommendations, alerts, reports, risk prediction and process improvement. |

# 4. PMO / Portfolio Management

Objective: Allow an organization to control multiple projects at the same time, including health, priority, cost, risk, capacity, progress and dependencies across the portfolio.

## Questions this module must answer

Which projects are green, yellow or red?

Which projects are delayed or over budget?

Where are the highest portfolio risks?

Which resources are overloaded?

Which projects should be prioritized, paused or escalated?

Which projects depend on other projects?

## Functional components

Portfolio dashboard

Project health scoring

Project prioritization

Cross-project risk view

Cross-project budget view

Shared resource capacity

Portfolio roadmap

Executive summary by portfolio

| Area | Details |
| --- | --- |
| Primary inputs | Projects Budgets Risks Schedules Resources Issues Change requests Status reports |
| Module outputs | Portfolio health Executive report Priority list Capacity warning Risk exposure by project Budget variance by project |
| Visualizations | Portfolio health dashboard Bubble chart by value/cost/risk Timeline roadmap Risk heatmap Budget variance chart Resource capacity chart |
| Automation / AI | Identify projects at risk Recommend prioritization Explain why a project is red Generate executive portfolio report |
| Connections with other modules | Projects Budget Risk Resource management Reports AI Super PM |
| Recommended MVP scope | Project list Health status Basic portfolio dashboard Project status summary Risk and budget indicators |

## Future / advanced version

Advanced portfolio scoring

Scenario planning

Resource optimization

Capital planning

Program management hierarchy

# 5. Project Charter and Initiation

Objective: Guide the user through project definition before execution begins, ensuring clear scope, purpose, business case, goals, stakeholders, success criteria and initial risks.

## Questions this module must answer

Why is this project being done?

What problem or opportunity does it address?

What is in scope and out of scope?

Who approves the project?

What are the high-level risks, assumptions and constraints?

How will success be measured?

## Functional components

Project charter wizard

Business case builder

Goal definition

High-level deliverables

Scope and exclusions

Assumptions and constraints

Initial stakeholder list

High-level budget and timeline

Approval workflow

| Area | Details |
| --- | --- |
| Primary inputs | Project idea Business problem Sponsor input Stakeholder input High-level cost and benefit assumptions |
| Module outputs | Project charter Business case Initial scope statement Approval request Initial stakeholder register Initial risk list |
| Visualizations | Charter canvas Business case summary Benefits vs cost chart Scope map Approval status view |
| Automation / AI | Draft charter Rewrite goals as SMART goals Identify missing information Suggest risks and assumptions Generate sponsor-ready summary |
| Connections with other modules | Stakeholders Communication plan Risks Budget Document control Change control |
| Recommended MVP scope | Project creation Charter wizard Goals Scope Deliverables Success criteria Approval status |

## Future / advanced version

Portfolio intake scoring

Project selection model

Strategic alignment analysis

Benefits realization tracking

# 6. Stakeholder Management

Objective: Identify, classify and manage all people or groups affected by the project, including their influence, interest, communication needs, decision authority and engagement strategy.

## Questions this module must answer

Who is affected by the project?

Who approves decisions?

Who must be consulted?

Who only needs to be informed?

Who has high influence and high interest?

What communication style does each stakeholder require?

## Functional components

Stakeholder register

Power/interest matrix

RACI chart

Stakeholder engagement plan

Communication preferences

Stakeholder risk indicators

Backup contacts

| Area | Details |
| --- | --- |
| Primary inputs | Project charter Team members Sponsors Clients Vendors Finance Operations Legal/compliance contacts |
| Module outputs | Stakeholder map RACI matrix Communication profile Engagement strategy Stakeholder risk warnings |
| Visualizations | Power/interest matrix RACI grid Stakeholder communication matrix Engagement heatmap |
| Automation / AI | Recommend engagement strategy Detect missing stakeholders Suggest communication frequency and detail level Flag stakeholders not updated recently |
| Connections with other modules | Communication plan Change control Decision log Risk management Reports |
| Recommended MVP scope | Stakeholder register RACI chart Power/interest matrix Communication preferences |

## Future / advanced version

Sentiment tracking

Stakeholder influence trend

Automated stakeholder update personalization

# 7. Communication Plan Management

This module turns the course communication planning concepts into a living system. It should not be a static spreadsheet. It must plan, execute, track and improve project communication. The guiding workflow is: Identify -> Document -> Develop -> Execute -> Check In -> Improve.

The right information, to the right stakeholder, through the right channel, at the right time, with the right evidence.

## Communication plan wizard

Identify stakeholders using the stakeholder map and RACI chart.

Define who needs to be informed at each point of the project lifecycle.

Define frequency, channel, detail level, owner, backup owner and key dates.

Define the goal of each communication: update, approval, feedback, clarification, escalation or decision confirmation.

Identify barriers such as time zones, language, privacy, access, executive response delays and technical limitations.

Add notes, reminders, backup plans, copy rules, access rules and document links.

Test important communications before sending.

Check effectiveness and improve the plan over time.

| Field | Purpose |
| --- | --- |
| Type of Communication | Newsletter, daily stand-up, status report, risk update, change approval, vendor update, budget review, launch announcement, lessons learned. |
| Recipients | Core team, sponsor, PMO, executive stakeholders, client, vendor, finance, procurement, legal, operations. |
| Frequency | Daily, weekly, monthly, bi-weekly, ad hoc, event-based, phase-based. |
| Key Dates | Specific dates, recurrence rules, decision deadlines, launch dates, review windows. |
| Delivery Method | Email, Teams, Slack, dashboard, meeting, PDF, in-person, video conference, system notification. |
| Goal | Provide update, request approval, request feedback, clarify issue, resolve problem, escalate risk, confirm decision. |
| Resource Links | Documents, meeting notes, dashboards, folders, reports, change requests, decision evidence. |
| Notes | CC rules, backup contacts, translation needs, special formatting, access limitations, reminder instructions. |

| Capability | Description |
| --- | --- |
| Stakeholder Profile | Role, RACI role, influence, interest, preferred channel, detail level, language, time zone, expected response time, backup contact and communication barriers. |
| Communication Goal | Every communication must state whether it informs, requests a decision, requests feedback, resolves a problem or escalates a risk. |
| Priority Flags | Normal, important, urgent, decision required, approval required, escalation, budget impact, schedule impact, risk impact. |
| Communication Test Checklist | Recipients confirmed, links tested, attachments included, correct document version, meeting link works, access verified, call to action clear, sensitive information reviewed. |
| Feedback Loop | Anonymous surveys, polls, meeting feedback, one-on-one check-ins, acknowledgement tracking and sentiment analysis. |
| Oversharing / Undersharing Detection | Detect stakeholders receiving too much, too little, outdated or incorrectly formatted information. |

## Communication plan dashboard

Upcoming communications

Overdue communications

Communications requiring response

Communications requiring approval

Stakeholders not updated recently

Change-related communications

Documents pending review

Feedback pending

Communication effectiveness score

| Area | Details |
| --- | --- |
| Primary inputs | Stakeholders RACI matrix Communication preferences Project schedule Risks Change requests Documents Meetings Email/chat items |
| Module outputs | Communication plan Communication matrix Scheduled communications Feedback records Communication health score Communication improvement actions |
| Visualizations | Communication timeline Stakeholder communication matrix Communication coverage heatmap Feedback dashboard Communication effectiveness scorecard |
| Automation / AI | Recommend channel and detail level Detect missing stakeholders Detect oversharing/undersharing Draft project messages Generate stakeholder updates Suggest follow-up actions |
| Connections with other modules | Stakeholders RACI Change control Document control Risk management Reports AI Super PM |
| Recommended MVP scope | Communication plan wizard Communication matrix Manual communication log Stakeholder preferences Basic feedback tracking Dashboard with overdue and upcoming communications |

# 8. Communication Intelligence Hub

Objective: Centralize and link emails, meetings, chat messages, decisions, action items and evidence to the exact project, task, risk, issue, change, budget item, material, supplier, stakeholder or process step they affect.

## Questions this module must answer

Where was this discussed?

Who approved it?

Which email, meeting or chat created this action?

Which communication supports this decision?

Which task, risk or change was affected?

What is the latest context?

## Functional components

Communication inbox

Project communication timeline

Email/thread linking

Meeting management

Meeting minutes

Action items from communications

Decision log

Communication traceability matrix

AI communication insights

| Area | Details |
| --- | --- |
| Primary inputs | Emails Outlook/Gmail threads Slack/Teams messages Calendar events Meeting notes Manual notes Attachments Documents |
| Module outputs | Linked communication records Action items Decisions Risks Issues Change requests Evidence trail |
| Visualizations | Communication timeline Traceability matrix Decision timeline Action item board Evidence map |
| Automation / AI | Extract action items Detect decisions Detect risks/issues/changes Summarize threads Generate meeting minutes Suggest links to project objects |
| Connections with other modules | Communication plan Tasks Risks Issues Changes Documents Stakeholders Reports |
| Recommended MVP scope | Manual log Meeting notes Decision log Action items Basic email/link capture |

## Future / advanced version

Gmail integration

Outlook/Teams integration

Slack integration

AI thread summarization

Automatic evidence linking

# 9. Document Control

Objective: Organize project documents by phase, type, status, owner, version, approval and relationship to project objects, so users always know which document is current and what decision or change created it.

## Questions this module must answer

Where is the current approved document?

Who owns it?

What version is valid?

Which change request updated it?

Who approved it?

Which communications or meetings reference it?

Who has access?

## Functional components

Project document repository

Folder structure by lifecycle phase

Document metadata

Version control

Approval status

Document links to tasks/risks/changes

Access control

Document review dates

| Area | Details |
| --- | --- |
| Primary inputs | Uploaded files Generated reports Meeting minutes Change requests Risk registers Budget reports ERP documents Drive/SharePoint links |
| Module outputs | Approved document library Version history Review reminders Document approval workflow Document evidence links |
| Visualizations | Repository tree Document status board Version history timeline Approval workflow view |
| Automation / AI | Warn if outdated version is being sent Suggest documents required by project phase Summarize documents Detect missing approvals |
| Connections with other modules | Communication plan Change control Meetings Decision log Reports Security |
| Recommended MVP scope | Document repository Document metadata Version field Status field Manual upload/link Basic approvals |

## Future / advanced version

Google Drive integration

SharePoint/OneDrive integration

Automated version comparison

AI document review checklist

# 10. Change Control

Objective: Formalize any change to scope, schedule, budget, risk, materials, quality or process, including its source, impact analysis, approvals, communication plan, implementation and closure.

## Questions this module must answer

What changed?

Why did it change?

Who requested it?

Where is the evidence?

What is the impact on scope, schedule, budget, risk, materials and documents?

Who approved or rejected it?

Was the change communicated?

## Functional components

Change request log

Change request form

Impact analysis

Approval workflow

Decision evidence

Change communication plan

Implementation tasks

Updated document list

| Area | Details |
| --- | --- |
| Primary inputs | Emails Meetings Stakeholder requests Issues Risks Budget variance Material shortage Process bottlenecks |
| Module outputs | Approved/rejected/deferred change requests Budget/schedule/scope impact Decision log entries Updated documents Communication requirements |
| Visualizations | Change control board Change impact chart Approval workflow view Change timeline Scope/budget/schedule impact dashboard |
| Automation / AI | Detect possible change requests from communications Draft impact analysis Recommend approvers Generate change notification Identify documents to update |
| Connections with other modules | Communication hub Document control Budget Schedule Risks Tasks Reports |
| Recommended MVP scope | Change request form Status workflow Impact fields Approver field Link to communication evidence |

## Future / advanced version

Multi-level approvals

Change board automation

Baseline comparison

Advanced audit trail

# 11. Task & Schedule Management

Objective: Manage project work through tasks, dependencies, milestones, deliverables, owners, status, dates, priorities, blockers and schedule impact.

## Questions this module must answer

What work needs to be done?

Who owns it?

When should it start and finish?

What depends on what?

What is blocked?

Which tasks are on the critical path?

Which tasks affect budget, risk, material demand or stakeholder communication?

## Functional components

Task board

Milestones

Deliverables

WBS

Dependencies

Calendar view

Gantt chart

Critical path

Task comments

Blocked task alerts

| Area | Details |
| --- | --- |
| Primary inputs | Project charter Deliverables WBS Resource plan Materials plan Risk register Change requests |
| Module outputs | Task plan Schedule baseline Progress updates Milestone status Delay alerts Action items |
| Visualizations | Kanban board Gantt chart WBS tree Calendar Critical path view Milestone tracker |
| Automation / AI | Convert deliverables into tasks Suggest dependencies Detect schedule delays Recommend recovery actions Generate task summaries |
| Connections with other modules | Budget Materials Risks Issues Communication BPM Reports |
| Recommended MVP scope | Task board Milestones Basic dependencies Due dates Owners Statuses Simple Gantt |

## Future / advanced version

Critical path engine

Resource leveling

Advanced scheduling

What-if scenarios

# 12. Budget Management

Objective: Control project budget from baseline to actuals and forecast, including labor, materials, vendors, procurement, change impacts and variance analysis.

## Questions this module must answer

What was the approved budget?

What has been spent?

What is planned vs actual?

What is the forecast at completion?

Which cost category is over budget?

Which change request increased cost?

Which materials or vendors are driving variance?

## Functional components

Budget baseline

Cost categories

Planned cost

Actual cost

Forecast cost

Cost variance

Burn rate

Contingency

Change cost impact

ERP actuals import

| Area | Details |
| --- | --- |
| Primary inputs | Initial budget Task costs Labor costs Material costs Vendor invoices Purchase orders ERP actuals Change requests |
| Module outputs | Budget dashboard Variance analysis Forecast at completion Budget alerts Cost reports Change impact summary |
| Visualizations | Planned vs actual chart Budget burn rate Cost variance by category S-curve Earned value dashboard |
| Automation / AI | Explain budget variance Forecast overrun Suggest corrective actions Generate budget summary Identify cost risk |
| Connections with other modules | ERP integration Materials Tasks Change control Reports AI Super PM |
| Recommended MVP scope | Budget baseline Budget categories Manual actuals Variance dashboard Change impact field |

## Future / advanced version

Earned Value Management

ERP actual cost sync

Invoice matching

Predictive budget forecasting

# 13. Risk Management

Objective: Identify, score, monitor and respond to project risks, including triggers, owners, mitigation, contingency, cost impact, schedule impact and links to tasks, materials, vendors or processes.

## Questions this module must answer

What could go wrong?

How likely is it?

What is the impact?

Who owns it?

What is the mitigation plan?

What trigger activates the response?

Which task, budget item, material or vendor is affected?

## Functional components

Risk register

Risk categories

Probability/impact scoring

Risk owner

Mitigation plan

Contingency plan

Triggers

Risk status

Risk escalation

| Area | Details |
| --- | --- |
| Primary inputs | Stakeholder input Tasks Materials Vendors Budget variance Issues Communications BPM bottlenecks |
| Module outputs | Risk score Risk heatmap Mitigation tasks Escalation communications Risk reports |
| Visualizations | Risk matrix Risk exposure trend Top risks Risk by category Risk burndown chart |
| Automation / AI | Suggest risks from project data Recommend mitigation Detect risk triggers Generate risk communication Explain risk exposure |
| Connections with other modules | Tasks Issues Change control Communication plan Budget Materials Reports |
| Recommended MVP scope | Risk register Probability/impact scoring Owner Mitigation Status Risk matrix |

## Future / advanced version

Predictive risk detection

Cross-project risk analytics

Risk simulation

# 14. Issue Management

Objective: Track active problems that are already happening, assign owners, manage resolution plans, link issues to tasks, risks, changes, communications and documents.

## Questions this module must answer

What problem is happening now?

Who owns the resolution?

How urgent is it?

What task or milestone is blocked?

Does it require a change request?

Was it communicated?

What evidence supports it?

## Functional components

Issue log

Issue priority

Owner assignment

Resolution plan

Escalation

Root cause

Related risk/change/task

Issue aging

| Area | Details |
| --- | --- |
| Primary inputs | Team updates Meetings Emails Chat messages Task blockers Material shortages Vendor delays Quality defects |
| Module outputs | Issue resolution status Escalation notifications Change requests Updated tasks Lessons learned |
| Visualizations | Issue board Issue aging chart Open issues by owner Blocker dashboard Root cause summary |
| Automation / AI | Detect issues from communications Suggest resolution actions Recommend escalation Summarize issue history |
| Connections with other modules | Tasks Risk Change control Communication hub Documents Reports |
| Recommended MVP scope | Issue log Priority/status Owner Due date Resolution plan Link to task/risk/change |

## Future / advanced version

Root cause analytics

AI resolution recommendations

Recurring issue detection

# 15. BPM / Process Improvement

Objective: Allow each project to map, measure and improve business processes, not just complete tasks. The app should identify bottlenecks, cycle time, rework, approval delays and improvement opportunities.

## Questions this module must answer

Which process supports this project?

What are the process steps?

Who owns each step?

Where is the bottleneck?

How long should each step take vs actual?

Which process delay affects the project schedule or budget?

## Functional components

Process map

Process steps

Owners

Expected duration/SLA

Actual duration

Swimlane view

Bottleneck detection

Process improvement actions

Rework tracking

| Area | Details |
| --- | --- |
| Primary inputs | Project workflows Approval steps Procurement process Material request process Issue resolution process Change control process |
| Module outputs | Process map Bottleneck alerts Cycle time metrics Improvement backlog Process-related risks or issues |
| Visualizations | BPMN-style diagram Swimlane diagram Cycle time dashboard Bottleneck chart Process efficiency score |
| Automation / AI | Recommend process improvements Detect approval delays Suggest automation Identify rework patterns Connect process delays to risks |
| Connections with other modules | Tasks Change control Materials Issues Risks Reports AI Super PM |
| Recommended MVP scope | Process builder Process steps Owners Expected duration Actual duration Basic bottleneck dashboard |

## Future / advanced version

BPMN modeling

Process mining

SLA automation

Workflow automation engine

# 16. Materials & Inventory Management

Objective: Connect project tasks and milestones with required materials, available inventory, consumption, reservations, suppliers, purchase requests and shortage alerts.

## Questions this module must answer

Which materials are required?

Which task or milestone needs them?

Are they available?

Where are they located?

What is reserved?

What has been consumed?

What must be purchased?

Could a shortage delay the project?

## Functional components

Material catalog

Project material requirements

Inventory locations

Material reservations

Consumption tracking

Supplier tracking

Purchase requests

Purchase orders

Delivery dates

Shortage alerts

| Area | Details |
| --- | --- |
| Primary inputs | Material list Task requirements Inventory data Supplier data Purchase orders ERP stock Warehouse data |
| Module outputs | Material plan Availability status Shortage alerts Consumption report Supplier delivery status Material cost by project |
| Visualizations | Material availability dashboard Required vs available chart Shortage risk view Supplier delivery performance Material cost chart |
| Automation / AI | Predict shortages Suggest reorder Connect shortage to schedule risk Recommend alternative supplier Generate procurement alerts |
| Connections with other modules | Tasks Schedule Budget Risks ERP integration Vendors Reports |
| Recommended MVP scope | Material catalog Project materials Inventory availability Manual transactions Shortage alerts |

## Future / advanced version

ERP inventory sync

Barcode/QR scanning

Warehouse management integration

Automated procurement

# 17. ERP Integration Layer

Objective: Provide a flexible connector architecture that allows the platform to import or synchronize project data from ERP and operational systems without depending on a single vendor.

## Questions this module must answer

Where does actual cost come from?

How do we import inventory?

Can purchase orders feed the project?

Can vendors and invoices be synchronized?

How often should data refresh?

What system is the source of truth?

## Functional components

Manual entry

CSV/Excel upload

API connectors

Database connectors

Webhooks

Scheduled sync

Connection mapping

Sync logs

Error handling

| Area | Details |
| --- | --- |
| Primary inputs | ERP budget data Actual cost Purchase orders Inventory Vendors Invoices Labor cost Cost centers Delivery status |
| Module outputs | Imported budget actuals Inventory updates PO status Vendor data Sync logs Data validation alerts |
| Visualizations | Connector status dashboard Sync history Data mapping view Import error dashboard |
| Automation / AI | Map imported fields Detect anomalies Suggest missing mappings Summarize sync failures Validate data quality |
| Connections with other modules | Budget Materials Procurement Reports AI Super PM Security |
| Recommended MVP scope | CSV/Excel import Generic API connector structure Sync log Basic mapping table |

## Future / advanced version

SAP, Oracle, Microsoft Dynamics, NetSuite, QuickBooks, Odoo, Zoho and custom ERP connectors

# 18. Reports & Dashboards

Objective: Transform project data into useful dashboards, status reports, executive summaries and control views for PMs, teams, stakeholders and PMO leadership.

## Questions this module must answer

What is the project health?

What changed this week?

What risks are critical?

What budget variance exists?

What decisions are pending?

What communications are overdue?

What documents require approval?

What actions must happen next?

## Functional components

Project dashboard

Portfolio dashboard

Weekly status report

Executive report

Risk report

Budget report

Change report

Communication report

Materials report

Closing report

| Area | Details |
| --- | --- |
| Primary inputs | Tasks Schedule Budget Risks Issues Changes Communications Documents Materials ERP actuals |
| Module outputs | Dashboards PDF/Word reports Email summaries Executive briefings Alerts KPIs |
| Visualizations | Health scorecards S-curves Risk heatmaps Budget variance charts Communication timelines Portfolio roadmap |
| Automation / AI | Generate weekly status report Summarize project health Explain red/yellow indicators Draft executive update Recommend next actions |
| Connections with other modules | All modules AI Super PM Communication plan Document control |
| Recommended MVP scope | Project dashboard Portfolio dashboard Weekly status report generator Basic exports |

## Future / advanced version

Custom dashboard builder

Automated report distribution

BI connector

Advanced analytics

# 19. AI Super Project Manager

Objective: Act as an intelligent project analyst that understands the project context, detects problems, generates project artifacts, recommends corrective actions and assists communication and reporting.

## Questions this module must answer

Why is this project at risk?

What should the PM do next?

What risks are emerging?

Which stakeholder needs an update?

What change may be required?

What process is causing delay?

What material shortage could affect the schedule?

## Functional components

AI assistant panel

AI insights feed

Project health explanation

Risk suggestions

Mitigation suggestions

Report generation

Communication drafting

Meeting minutes

Lessons learned generation

| Area | Details |
| --- | --- |
| Primary inputs | All project data Tasks Schedule Risks Issues Budget Materials Communications Documents ERP data |
| Module outputs | Recommendations Draft artifacts Alerts Status reports Risk mitigations Process improvement ideas Stakeholder updates |
| Visualizations | AI insight cards Project health explanation panel Recommendation backlog Risk and issue prediction feed |
| Automation / AI | Generate charter Create tasks from deliverables Analyze budget variance Detect bottlenecks Extract decisions Summarize communications Generate reports |
| Connections with other modules | Every module Reports Communication hub BPM ERP integration |
| Recommended MVP scope | AI report generator Risk suggestions Communication summarization Project health explanation |

## Future / advanced version

Predictive analytics

Scenario planning

Autonomous PM recommendations

Natural language project query

# 20. Security, Roles & Permissions

Objective: Protect sensitive project, financial, communication and document data using role-based access, project-level permissions, audit logs and integration controls.

## Questions this module must answer

Who can see financial data?

Who can view sensitive communications?

Who can approve changes?

Who can edit documents?

Who can connect an ERP?

What activity must be audited?

## Functional components

Organizations

Roles

Permissions

Project access

Document access

Communication access rules

Integration permissions

Audit log

Sensitive data flags

| Area | Details |
| --- | --- |
| Primary inputs | Users Teams Projects Documents Communications ERP data Role assignments |
| Module outputs | Secure access Audit history Restricted views Approval controls Compliance support |
| Visualizations | Permission matrix Audit log timeline Access dashboard |
| Automation / AI | Recommend least-privilege roles Detect unusual access Warn before sharing sensitive data |
| Connections with other modules | All modules Document control Communication hub ERP integration |
| Recommended MVP scope | Organization roles Project roles Basic permissions Audit log Restricted documents |

## Future / advanced version

SSO

SCIM provisioning

advanced compliance, encryption policies, legal hold

# 21. Database Structure

The first database version should be modular, relational and traceability-focused. The most important design rule is that every major object can be linked to other project objects through relationship tables.

| Domain | Suggested tables |
| --- | --- |
| Core | organizations users teams team_members roles permissions projects project_portfolios |
| Initiation | project_charters project_goals project_deliverables project_assumptions project_constraints project_approvals |
| Stakeholders | stakeholders raci_matrix stakeholder_preferences stakeholder_engagements |
| Communication | communication_plans communication_plan_items communication_recipients communication_barriers communication_preferences communication_items communication_threads communication_links communication_feedback |
| Meetings & Decisions | meetings meeting_attendees meeting_notes meeting_decisions action_items decision_log |
| Documents | documents document_versions document_links document_approvals document_access_rules |
| Project Control | project_tasks task_dependencies project_milestones risks issues change_requests change_approvals |
| Budget | budgets budget_categories budget_actuals cost_forecasts change_cost_impacts |
| BPM | processes process_steps process_metrics process_improvements process_links |
| Materials | materials project_materials inventory_locations inventory_transactions suppliers purchase_requests purchase_orders |
| Integrations | erp_connections erp_field_mappings erp_sync_logs external_system_links |
| AI & Reports | status_reports ai_recommendations ai_insights lessons_learned report_exports |

## Critical relationship tables

communication_links: links emails, meetings or chat items to projects, tasks, risks, issues, changes, budget items, materials, stakeholders and process steps.

document_links: links documents to project objects and decisions.

change_request_links: links changes to scope, tasks, budget, risks, materials, documents and communications.

process_links: links BPM steps to tasks, risks, issues, changes and materials.

ai_recommendation_links: links AI insights to the objects that caused the recommendation.

# 22. MVP Roadmap

| Phase | Scope |
| --- | --- |
| MVP 1 - Core Project Control | Organizations, users, projects, project charter, stakeholders, RACI, tasks, milestones, risk register, issue log, budget baseline, project dashboard, manual communication log, decision log and document repository. |
| MVP 2 - Communication & Change Control | Communication plan wizard, communication matrix, meeting notes, action items from meetings, change requests, approval workflow, document versioning and communication dashboard. |
| MVP 3 - BPM & Process Improvement | Process builder, process steps, owners, SLA/expected duration, actual duration, bottleneck dashboard, improvement actions and process-related risks/issues. |
| MVP 4 - Materials & Inventory | Material catalog, project material requirements, inventory availability, material consumption, suppliers, purchase requests, purchase orders and shortage alerts. |
| MVP 5 - Integrations | CSV/Excel imports, generic API connector, basic Gmail/Google Calendar/Drive integration, later Outlook/Teams/SharePoint/Slack, ERP sync logs. |
| MVP 6 - Advanced PMO & AI | Portfolio dashboard, cross-project risk/budget/capacity analytics, AI recommendations, predictive alerts, executive reports and scenario planning. |

# 23. Navigation and UX

The navigation must feel like a professional SaaS control center, not a generic task board. It should keep PM methodology visible while allowing users to work quickly.

| Navigation area | Purpose |
| --- | --- |
| Global Dashboard | Portfolio health, alerts, overdue actions, upcoming communications, approvals, risks and budget warnings. |
| Portfolio / PMO | Multiple projects, roadmap, capacity, risks, budgets and executive view. |
| Projects | Project list, project detail, health status, lifecycle stage, owner and priority. |
| Lifecycle | Initiation, Planning, Execution, Monitoring & Controlling, Closing. |
| Tasks & Schedule | Task board, Gantt, milestones, dependencies, WBS and calendar. |
| Budget | Baseline, actuals, forecast, variance, burn rate and change impacts. |
| Risks & Issues | Risk register, issue log, heatmaps, mitigations and escalations. |
| Change Control | Change requests, impact analysis, approvals and change communications. |
| Communication | Communication plan, communication hub, meetings, action items, decision log and feedback. |
| Documents | Repository, versions, approvals, access and links to project objects. |
| BPM Processes | Process maps, steps, bottlenecks and improvement actions. |
| Materials & Inventory | Materials, availability, consumption, suppliers and purchase requests. |
| ERP Connectors | Imports, API connections, mappings and sync logs. |
| Reports | Status reports, executive reports, risk reports, budget reports and closing reports. |
| AI Super PM | AI insights, recommendations, draft generation, risk suggestions and report generation. |
| Settings | Organization, users, roles, permissions, integrations and templates. |

# 24. Pending decisions before the final prompt

Before writing the final development prompt, the following product decisions should be clarified. These decisions will determine the technical architecture, MVP scope and implementation sequence.

Primary target customer: students/new PMs, PMOs, construction/installation teams, operations teams, technology teams or small companies.

First MVP focus: Project control, communication/change control, budget/risk, or PMO portfolio dashboard.

Initial integrations: Google ecosystem first, Microsoft ecosystem first, or manual/CSV first.

Document storage strategy: internal storage, Google Drive/SharePoint link-first, or hybrid.

Communication storage policy: metadata and summary only by default, or full message body with explicit permission.

ERP integration sequence: CSV/Excel import first, then generic API, then named ERP connectors.

Budget depth: simple planned vs actual first, or full earned value management from the beginning.

BPM depth: simple process steps first, or full BPMN-style process modeling.

AI behavior: assistant only, recommendation engine, report generator, or all three in phases.

Technology stack: Supabase/Postgres, React/Next.js, Node/Python backend, storage, auth and AI provider strategy.

Final product definition: an intelligent project control system where every task, communication, change, risk, budget item, document, material and decision is connected, traceable and actionable.

# Appendix A - Documentation Plan Formats and Template Tables

Source: Project-plan.xlsx - Plant Pals Operations & Training Plan

This appendix adds the spreadsheet formats that must be accessible from the platform's Document Control and Communication Plan modules. Each format should be stored as a managed project document, versioned, linked to the correct module, and connected to the related project records.

How these formats should work inside the platform

Each template must have a document type, owner, access level, status, current approved version, and related project phase.

Each template should be linkable to project records such as tasks, risks, budget items, communication items, decisions, and change requests.

The app should allow these formats to be uploaded, generated, exported, versioned, reviewed, approved, archived, and referenced in reports.

When a change request modifies scope, schedule, budget, communication, or risk, the related template should be flagged for review and version update.

The tables below preserve the Plant Pals workbook content as editable Word tables for product review. The Gantt date grid is represented by the task table for readability; the application should still support a full Gantt visualization in the Schedule module.

## A.1 Template Access Matrix

| Source Format / Sheet | App Module | Project Phase | Purpose | Primary Owner | Key Records Linked |
| --- | --- | --- | --- | --- | --- |
| Documentation Dashboard / Key Docs | Document Control | Initiation, Planning, Control | Create a structured index of all core project documents and resources. | Project Manager | Charter, SoW, risk plan, schedule, budget, communication plan, shared folder, RACI chart |
| Project Schedule / Gantt | Task & Schedule Management | Planning, Execution, Monitoring & Controlling | Track milestones, tasks, owners, start dates, due dates, duration, and completion percentage. | Project Manager / Task Owners | Tasks, milestones, dependencies, schedule baseline, status reports |
| Budget | Budget Management | Planning, Monitoring & Controlling | Track target budget, actual/final spend, labor, materials, fixed costs, reserve buffer, and under/over variance. | Financial Analyst / Project Manager | Budget baseline, actual costs, materials, labor, change requests |
| Communication Plan | Communication Plan Management | Planning, Execution, Monitoring & Controlling | Define recipients, communication type, frequency, owner, key dates, delivery method, goals, resource links, and notes. | Project Manager / Communication Owner | Stakeholders, RACI, meetings, decision log, document links, change communications |

## A.2 Project Documentation Dashboard / Key Docs

Purpose: index the core project documents and make them accessible from the document repository, communication plan, change control, and project dashboard.

| Key Docs | Description |
| --- | --- |
| Project charter | An overview of the project, key elements and expectations |
| Statement of work | Identifies the work that is included in the project and the pricing that was quoted initially. |
| Risk management plan | Identifies the potential risks to the project, their likelihood, and how you plan to mitigate them if they become realized. |
| Schedule | Identifies the planned schedule as well as any changes through out the project lifecycle. |
| Budget | Identifies the planned budget as well as any over and under runs. Allows you to estimate the cost at completion. |
| Communication plan | Identifies how often, what type of communication method, and what information your stakeholders needs to know |
| Shared folder | Folder with all relevant documentation |
| RACI chart | Identifies who is responsible, accountable, consulted and informed within the project. |

## A.3 Project Schedule / Gantt Task Table

Schedule metadata from the workbook.

| Title | Plant Pals Operations and Training Plan |
| --- | --- |
| Project Manager | Project Manager |
| Company Name | Office Green |
| Creation Date | 02/15 |

Task table extracted from the Gantt schedule template.

| TASK ID NUMBER | MILESTONES & TASKS | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Establish a plant delivery and logistics plan |  |  |  |  |  |
| 1.1 | Source packaging materials | Fulfillment Director | 3/1 | 3/12 | 10 | 0 |
| 1.2 | Hire delivery drivers | HR Specialist | 3/15 | 3/26 | 10 | 0 |
| 1.3 | Calculate delivery fees | Financial Analyst | 3/29 | 4/9 | 10 | 0 |
| 2 | Select and install supply chain software and equipment |  |  |  |  |  |
| 2.1 | Supervise vendor setup of inventory management and fulfillment software | Inventory manager | 4/12 | 4/14 | 3 | 0 |
| 2.2 | Supervise vendor installation of fulfillment equipment | Fulfillment Director | 4/15 | 4/16 | 2 | 0 |
| 2.3 | Determine internal safety protocols for equipment | Quality Assurance Tester | 4/19 | 4/30 | 10 | 0 |
| 3 | Develop and launch an employee training program |  |  |  |  |  |
| 3.1 | Develop training sessions | HR Specialist | 5/3 | 5/14 | 10 | 0 |
| 3.2 | Train employees to use the software and equipment | Training Manager | 5/17 | 5/28 | 20 | 0 |
| 3.3 | Monitor employee progress and improve training processes | Training Manager | 5/31 | 6/11 | 10 | 0 |

## A.4 Budget Table

Budget summary.

| Target Budget | 62000 |
| --- | --- |
| Actual / Final Spend | 0 |
| Under / Over | 62000 |

Budget detail by milestone, task, labor, materials, fixed cost, budget, actual, and under/over variance.

|  | LABOR |  |  | MATERIALS |  | FIXED COST | BUDGET | ACTUAL | UNDER/OVER |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| MILESTONES & TASKS | EMPLOYEE | HOURS | RATE | UNITS | $/UNIT(S) |  |  |  |  |
| Milestone 1: Establish a plant delivery and logistics plan |  |  |  |  |  |  |  |  |  |
| Task 1: Purchase delivery trucks | -- |  |  | 2 | 15000 |  | 30000 |  | -30000 |
| Task 2: Source packaging materials | -- |  |  | 1500 | 2 |  | 3000 |  | -3000 |
| Task 3: Pay delivery drivers | Delivery Drivers (2) | 160 | 15 |  |  |  | 2400 |  | -2400 |
|  |  |  |  |  |  | Total | 35400 | 0 |  |
| Milestone 2: Select and install supply chain management software and equipment |  |  |  |  |  |  |  |  |  |
| Task 1: Source vendor (includes set up, installation, and deployment of systems) | -- |  |  |  |  | 15000 | 15000 |  | -15000 |
|  |  |  |  |  |  | Total | 15000 | 0 |  |
| Milestone 3: Develop and launch an employee training program |  |  |  |  |  |  |  |  |  |
| Task 1: Develop training sessions | HR Specialist | 80 | 50 |  |  |  | 4000 |  | -4000 |
| Task 2: Train employees to use the software and equipment | Training Manager | 80 | 25 |  |  |  | 2000 |  | -2000 |
| Task 3: Monitor employee progress and improve training processes | Training Manager | 80 | 25 |  |  |  | 2000 |  | -2000 |
|  |  |  |  |  |  | Total | 8000 | 0 |  |
| Reserve buffer |  |  |  |  |  |  | 3600 |  |  |
| TOTAL |  |  |  |  |  |  | 62000 | 0 |  |

## A.5 Communication Plan Table

Communication plan table extracted from the Plant Pals employee training communication plan.

| Recipients | Type of Communication | Frequency | Sender/Owner | Key Dates | Delivery Method | Goal | Resource Links | Notes |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Core Team | Planning Meeting | Daily | Project Manager | Every day at 3pm | In Person | Project planning and task updates to make sure the team stays on track | [link to meeting agenda and notes] | If needed, check in with manager about any high-level questions before meetings. |
| Software and Equipment Vendor | Planning Meeting | One time | Core Team: HR Specialist & Training Manager | Half day, Friday before development of the training plan begins; confirm date and time three days in advance | In Person | Go over the training manual in order to create an effective training plan for Office Green's employees | [link to vendor SoW] | This meeting needs to take place before the end of the vendor's SoW. Make sure the HR Specialist & Training Manager check in with fulfillment and inventory team members about the outcome of the meeting. |
| Human Resources | Planning Check-In | Weekly | Core Team: HR Specialist | Also send reminders (via email) the day before each training | In Person | Project planning assistance; provide support during the training session |  | Additional communication on an as-needed basis |
| Facilities | Planning Check-In | Weekly | Core Team: Administrative Coordinator | Tuesdays at 2pm | Phone Call | Reserve rooms, spaces, and equipment needed for employee training | [link to room and equipment reservation form] |  |
| Print Shop | Planning Check-In | Weekly | Core Team: Administrative Coordinator | Thursdays, including the day before the event | Phone Call | Coordinate on the printing and delivery of training manuals for employees | [link to printing order form] |  |
| Office Green employees | Informational Update | Weekly | Core Team: Training Manager | Fridays, including the Friday before training sessions begin | Email (from company address) | Communicate schedules, locations, and other necessary details to trainees | [trainee email list] | Set up automated reminder emails |
| Office Green employees | Training | Daily | Core Team: Training Manager | Each day for ten days, starting at 10am | In Person | Train employees to use the supply chain management software and equipment | [link to training schedule] |  |
| Office Green employees | Survey | One time | Core Team: Training Manager | The first business day after trainings end, with two follow-up reminders | Email (from company address) | Post-training survey | [trainee email list] | Discuss results at next team meeting |
| Your Manager | Status Update | Weekly | Project Manager | Monday afternoons at 2pm | In Person | Update on event planning, ask questions, and get feedback |  | Come prepared with a brief update and specific questions |
| Senior Leaders: Director of Operations and the Director of Product (and CC your manager) | Status Update | One time | Project Manager | Debrief the week after the event | Email (from individual address) | High-level information and general updates | [link to folder with training notes and survey results] |  |

Product implication

These templates should become managed, searchable, and linkable document records rather than static files.

The Documentation Plan should expose these formats as reusable project templates and allow users to attach them to communications, meetings, change requests, risks, budget reviews, and closing reports.

The Communication Plan table should be treated as an active control object that generates reminders, meetings, action items, follow-ups, and communication effectiveness metrics.