## Overview
ProjectOps360° — Solo Builder Plan: Phase 0 + MVP-0
Purpose: Restructured WBS and sprint backlog for a one-person, AI-assisted build. This file replaces team-based ownership with a solo founder/developer execution model.
Decision | Value | Metric | Formula / Value
Execution model | Solo Founder / Solo Developer, AI-assisted | Total WBS tasks | 34
Primary wedge | Project Memory & Decision Traceability | Total estimated hours | 221
Phase 0 outcome | Secure technical foundation: auth, organization, project shell, RLS, i18n, AI service baseline | Phase 0 estimated hours | 91
MVP-0 outcome | Create project → log communication/meeting → extract decision/action items with AI → link evidence → retrieve decision later | MVP-0 estimated hours | 130
Sprint length | 2 weeks | Sprint 0 planned hours | 27
Planning rule | Maximum planned capacity = 70% of available hours; keep 30% buffer for debugging/rework | Sprint 1 planned hours | 24
i18n | Foundation from Phase 0 using next-intl; bilingual coverage phased | Sprint 2 planned hours | 26
AI | Transversal assistant with human-in-the-loop; no automatic critical changes | Sprint 3 planned hours | 22
Not included in MVP-0 | BPM, ERP, materials/inventory, portfolio PMO, advanced budget, advanced Gantt, full Gmail/Teams/Slack integrations | Sprint 4 planned hours | 28
|  | Sprint 5 planned hours | 20
|  | Sprint 6 planned hours | 26
|  | Sprint 7 planned hours | 26
|  | Sprint 8 planned hours | 22

## Solo_Capacity
Solo Builder Capacity Assumptions
Parameter | Value | Notes
Available hours per week | 20 | Change this value if your weekly availability changes.
Sprint length weeks | 2 | Recommended sprint length for solo execution.
Raw sprint capacity hours | 40 | Calculated.
Planning load | 0.7 | Plan only 70% of available time.
Planned sprint capacity hours | 28 | Maximum workload to commit per sprint.
Buffer percentage | 0.3 | Reserved for debugging, learning, rework, setup problems.
Buffer hours | 12 | Calculated.
Solo execution rule: do not fill more than the planned sprint capacity unless a task is very small or unavoidable. Protect the buffer.

## WBS_Solo
WBS ID | Workstream | Phase | Task | Detailed Description | Deliverable | Dependency IDs | Priority | Est. Hours | Sprint Target | Status | Owner | AI-Assisted? | Acceptance Reference | Notes
0.1 | Planning & Scope | Phase 0 | Confirm solo-builder scope | Freeze Phase 0 + MVP-0 scope around Project Memory & Decision Traceability. | Approved MVP-0 scope statement |  | P1 | 2 | Sprint 0 | Not Started | Founder / Solo Developer | Yes | AC-001 | Avoid expanding into full PMO.
0.2 | Planning & Scope | Phase 0 | Create single source of truth folder | Create official documentation folder structure and archive duplicate/old docs. | Source of truth folder | 0.1 | P1 | 2 | Sprint 0 | Not Started | Founder / Solo Developer | No | AC-002 | Use one current set of docs.
0.3 | Planning & Scope | Phase 0 | Define Definition of Done | Write DoD for Phase 0 and MVP-0 including manual QA, RLS checks, and demo criteria. | Definition of Done doc | 0.1 | P1 | 3 | Sprint 0 | Not Started | Founder / Solo Developer | Yes | AC-003 | Keep practical for solo builder.
0.4 | Planning & Scope | Phase 0 | Create project repo | Create GitHub repository, branch strategy, README, and initial project structure. | GitHub repo | 0.1 | P1 | 2 | Sprint 0 | Not Started | Founder / Solo Developer | Yes | AC-004 | Main/develop or trunk-based simple.
0.5 | Dev Environment | Phase 0 | Install Next.js + TypeScript app | Create Next.js app with TypeScript, App Router, ESLint, Tailwind. | Running frontend scaffold | 0.4 | P1 | 4 | Sprint 0 | Not Started | Founder / Solo Developer | Yes | AC-005 | Use stable starter stack.
0.6 | Dev Environment | Phase 0 | Install UI foundation | Install shadcn/ui, Lucide icons, base layout, theme colors, typography. | UI foundation | 0.5 | P1 | 5 | Sprint 0 | Not Started | Founder / Solo Developer | Yes | AC-006 | Apply soft green branding.
0.7 | i18n | Phase 0 | Install next-intl | Configure next-intl with English and Spanish message files. | i18n foundation | 0.5 | P1 | 4 | Sprint 0 | Not Started | Founder / Solo Developer | Yes | AC-007 | Foundation only, not full translation catalog.
0.8 | i18n | Phase 0 | Create language switcher | Add simple ES/EN switcher and persist preference in profile later. | Language switcher UI | 0.7 | P2 | 3 | Sprint 0 | Not Started | Founder / Solo Developer | Yes | AC-008 | Can be simple dropdown.
0.9 | Supabase | Phase 0 | Create Supabase project | Create Supabase project, local env variables, and connection keys. | Supabase project | 0.4 | P1 | 2 | Sprint 0 | Not Started | Founder / Solo Developer | No | AC-009 | Do not commit secrets.
0.10 | Supabase | Phase 0 | Create baseline DB schema | Create minimal tables for organizations, profiles, projects, stakeholders, communications, decisions, documents, links, ai_runs. | Migration scripts | 0.9 | P1 | 10 | Sprint 1 | Not Started | Founder / Solo Developer | Yes | AC-010 | Build only MVP-0 tables.
0.11 | Security | Phase 0 | Configure Supabase Auth | Set up email/password auth and protected app routes. | Working authentication | 0.9,0.5 | P1 | 6 | Sprint 1 | Not Started | Founder / Solo Developer | Yes | AC-011 | Magic link optional later.
0.12 | Security | Phase 0 | Implement organization membership model | Create membership table and helpers to retrieve user org context. | Org membership logic | 0.10,0.11 | P1 | 8 | Sprint 1 | Not Started | Founder / Solo Developer | Yes | AC-012 | Single org support acceptable initially.
0.13 | Security | Phase 0 | Create initial RLS policies | Add RLS for org-scoped access to MVP-0 tables. | RLS policies | 0.10,0.12 | P1 | 10 | Sprint 2 | Not Started | Founder / Solo Developer | Yes | AC-013 | RLS must block cross-org access.
0.14 | Security | Phase 0 | Create RLS smoke tests | Create manual/automated basic tests for org isolation. | RLS test checklist | 0.13 | P1 | 6 | Sprint 2 | Not Started | Founder / Solo Developer | Yes | AC-014 | Do at least manual SQL tests if automated tests take too long.
0.15 | AI Foundation | Phase 0 | Create AI service abstraction | Create backend AI service wrapper with provider abstraction, prompt registry skeleton, and ai_runs logging. | AI service baseline | 0.10 | P1 | 8 | Sprint 2 | Not Started | Founder / Solo Developer | Yes | AC-015 | No direct model calls from UI.
0.16 | AI Foundation | Phase 0 | Configure AI environment variables | Add secure model keys, server-only access, and local env documentation. | AI env setup | 0.15 | P1 | 2 | Sprint 2 | Not Started | Founder / Solo Developer | No | AC-016 | Secrets server-side only.
0.17 | Core UI | Phase 0 | Create app shell navigation | Create dashboard layout, sidebar, project area, settings placeholder. | App shell | 0.6,0.11 | P1 | 6 | Sprint 3 | Not Started | Founder / Solo Developer | Yes | AC-017 | Minimal but clean.
0.18 | Core UI | Phase 0 | Create project shell | Allow create/view one project with name, description, status, default language. | Project shell UI | 0.10,0.17 | P1 | 8 | Sprint 3 | Not Started | Founder / Solo Developer | Yes | AC-018 | First project can be manually created.
1.1 | MVP-0 Core | MVP-0 | Create stakeholder register basic | CRUD stakeholders with name, role, organization, language preference, communication preference. | Stakeholder register | 0.18 | P1 | 8 | Sprint 3 | Not Started | Founder / Solo Developer | Yes | AC-019 | No complex matrix yet.
1.2 | MVP-0 Core | MVP-0 | Create communication log manual | CRUD communication items: source, title, summary, date, sender, recipients, project, notes. | Communication log | 0.18,1.1 | P1 | 10 | Sprint 4 | Not Started | Founder / Solo Developer | Yes | AC-020 | Manual entry only; no Gmail/Teams yet.
1.3 | MVP-0 Core | MVP-0 | Create meeting notes screen | Allow logging meeting title, date, attendees, notes, linked project. | Meeting notes UI | 0.18,1.1 | P1 | 8 | Sprint 4 | Not Started | Founder / Solo Developer | Yes | AC-021 | Simple rich text optional.
1.4 | MVP-0 Core | MVP-0 | Create decision log | CRUD decisions with title, description, decision maker, date, source, impact area, evidence link. | Decision log | 1.2,1.3 | P1 | 10 | Sprint 4 | Not Started | Founder / Solo Developer | Yes | AC-022 | Decision must link to project.
1.5 | Documents & Evidence | MVP-0 | Create document/evidence repository basic | Upload or register document/evidence link with type, owner, status, project, language. | Evidence repository | 0.10,0.18 | P1 | 8 | Sprint 5 | Not Started | Founder / Solo Developer | Yes | AC-023 | Supabase Storage or external URL.
1.6 | Traceability | MVP-0 | Create traceability links table UI | Allow linking communication, meeting, decision, and document records. | Traceability links UI | 1.2,1.3,1.4,1.5 | P1 | 12 | Sprint 5 | Not Started | Founder / Solo Developer | Yes | AC-024 | At least decision-to-evidence and communication-to-decision.
1.7 | AI MVP | MVP-0 | AI extract decisions from meeting notes | Send meeting notes to AI and return suggested decisions requiring user confirmation. | AI decision extraction | 0.15,1.3,1.4 | P1 | 10 | Sprint 6 | Not Started | Founder / Solo Developer | Yes | AC-025 | Human confirmation required.
1.8 | AI MVP | MVP-0 | AI extract action items | Extract action items from communication/meeting notes and save as suggested follow-ups. | AI action item extraction | 0.15,1.2,1.3 | P1 | 8 | Sprint 6 | Not Started | Founder / Solo Developer | Yes | AC-026 | Can save to action_items or notes if tasks not built.
1.9 | AI MVP | MVP-0 | AI summarize communication history | Generate a project communication summary from existing communications and decisions. | AI summary | 1.2,1.4,0.15 | P2 | 8 | Sprint 6 | Not Started | Founder / Solo Developer | Yes | AC-027 | Must cite linked records in app UI.
1.10 | Search & Retrieval | MVP-0 | Create basic search | Search communications, meetings, decisions, and documents by keyword. | Basic search | 1.2,1.3,1.4,1.5 | P1 | 8 | Sprint 7 | Not Started | Founder / Solo Developer | Yes | AC-028 | Semantic search can come later.
1.11 | Dashboard | MVP-0 | Create MVP-0 project memory dashboard | Show recent communications, decisions, evidence items, unresolved AI suggestions, missing links. | Project memory dashboard | 1.2,1.4,1.5,1.6 | P1 | 10 | Sprint 7 | Not Started | Founder / Solo Developer | Yes | AC-029 | Dashboard answers: what happened, what was decided, where is evidence.
1.12 | Audit | MVP-0 | Add audit log for critical records | Log create/update/delete on decisions, documents, communication links, AI runs. | Audit logging | 0.10,1.4,1.5,1.6 | P2 | 8 | Sprint 7 | Not Started | Founder / Solo Developer | Yes | AC-030 | Critical for trust.
1.13 | QA | MVP-0 | Manual end-to-end scenario test | Test full vertical slice: create project → meeting → AI extract decision → link evidence → search decision. | E2E test evidence | 1.6,1.7,1.10,1.11 | P1 | 6 | Sprint 8 | Not Started | Founder / Solo Developer | No | AC-031 | Record screenshots or notes.
1.14 | QA | MVP-0 | Performance and AI cost smoke check | Measure page load, AI latency, token cost estimate for common actions. | Performance/cost notes | 1.7,1.8,1.9,1.11 | P2 | 4 | Sprint 8 | Not Started | Founder / Solo Developer | Yes | AC-032 | Simple spreadsheet or notes.
1.15 | Release | MVP-0 | Prepare demo script | Create a short demo narrative for MVP-0 wedge. | Demo script | 1.11,1.13 | P1 | 4 | Sprint 8 | Not Started | Founder / Solo Developer | Yes | AC-033 | Demo for validation interviews/design partners.
1.16 | Release | MVP-0 | Deploy MVP-0 preview | Deploy to Vercel, configure production Supabase env, basic smoke test. | Preview deployment | 0.17,1.13 | P1 | 8 | Sprint 8 | Not Started | Founder / Solo Developer | Yes | AC-034 | Shareable preview link.

## Sprint_Backlog
Backlog ID | Sprint | WBS ID | User Story / Task | Why it matters | Dependencies | Priority | Status | Owner | Est. Hours | Acceptance Ref | Demo Evidence | Notes | Sprint Capacity Check
BL-001 | Sprint 0 | 0.1 | Confirm solo-builder scope | Approved MVP-0 scope statement |  | P1 | Not Started | Founder / Solo Developer | 2 | AC-001 |  | Avoid expanding into full PMO. | Sprint | Planned Hours | Capacity | Over/Under
BL-002 | Sprint 0 | 0.2 | Create single source of truth folder | Source of truth folder | 0.1 | P1 | Not Started | Founder / Solo Developer | 2 | AC-002 |  | Use one current set of docs. | Sprint 0 | 27 | 28 | 1
BL-003 | Sprint 0 | 0.3 | Define Definition of Done | Definition of Done doc | 0.1 | P1 | Not Started | Founder / Solo Developer | 3 | AC-003 |  | Keep practical for solo builder. | Sprint 1 | 24 | 28 | 4
BL-004 | Sprint 0 | 0.4 | Create project repo | GitHub repo | 0.1 | P1 | Not Started | Founder / Solo Developer | 2 | AC-004 |  | Main/develop or trunk-based simple. | Sprint 2 | 26 | 28 | 2
BL-005 | Sprint 0 | 0.5 | Install Next.js + TypeScript app | Running frontend scaffold | 0.4 | P1 | Not Started | Founder / Solo Developer | 4 | AC-005 |  | Use stable starter stack. | Sprint 3 | 22 | 28 | 6
BL-006 | Sprint 0 | 0.6 | Install UI foundation | UI foundation | 0.5 | P1 | Not Started | Founder / Solo Developer | 5 | AC-006 |  | Apply soft green branding. | Sprint 4 | 28 | 28 | 0
BL-007 | Sprint 0 | 0.7 | Install next-intl | i18n foundation | 0.5 | P1 | Not Started | Founder / Solo Developer | 4 | AC-007 |  | Foundation only, not full translation catalog. | Sprint 5 | 20 | 28 | 8
BL-008 | Sprint 0 | 0.8 | Create language switcher | Language switcher UI | 0.7 | P2 | Not Started | Founder / Solo Developer | 3 | AC-008 |  | Can be simple dropdown. | Sprint 6 | 26 | 28 | 2
BL-009 | Sprint 0 | 0.9 | Create Supabase project | Supabase project | 0.4 | P1 | Not Started | Founder / Solo Developer | 2 | AC-009 |  | Do not commit secrets. | Sprint 7 | 26 | 28 | 2
BL-010 | Sprint 1 | 0.10 | Create baseline DB schema | Migration scripts | 0.9 | P1 | Not Started | Founder / Solo Developer | 10 | AC-010 |  | Build only MVP-0 tables. | Sprint 8 | 22 | 28 | 6
BL-011 | Sprint 1 | 0.11 | Configure Supabase Auth | Working authentication | 0.9,0.5 | P1 | Not Started | Founder / Solo Developer | 6 | AC-011 |  | Magic link optional later.
BL-012 | Sprint 1 | 0.12 | Implement organization membership model | Org membership logic | 0.10,0.11 | P1 | Not Started | Founder / Solo Developer | 8 | AC-012 |  | Single org support acceptable initially.
BL-013 | Sprint 2 | 0.13 | Create initial RLS policies | RLS policies | 0.10,0.12 | P1 | Not Started | Founder / Solo Developer | 10 | AC-013 |  | RLS must block cross-org access.
BL-014 | Sprint 2 | 0.14 | Create RLS smoke tests | RLS test checklist | 0.13 | P1 | Not Started | Founder / Solo Developer | 6 | AC-014 |  | Do at least manual SQL tests if automated tests take too long.
BL-015 | Sprint 2 | 0.15 | Create AI service abstraction | AI service baseline | 0.10 | P1 | Not Started | Founder / Solo Developer | 8 | AC-015 |  | No direct model calls from UI.
BL-016 | Sprint 2 | 0.16 | Configure AI environment variables | AI env setup | 0.15 | P1 | Not Started | Founder / Solo Developer | 2 | AC-016 |  | Secrets server-side only.
BL-017 | Sprint 3 | 0.17 | Create app shell navigation | App shell | 0.6,0.11 | P1 | Not Started | Founder / Solo Developer | 6 | AC-017 |  | Minimal but clean.
BL-018 | Sprint 3 | 0.18 | Create project shell | Project shell UI | 0.10,0.17 | P1 | Not Started | Founder / Solo Developer | 8 | AC-018 |  | First project can be manually created.
BL-019 | Sprint 3 | 1.1 | Create stakeholder register basic | Stakeholder register | 0.18 | P1 | Not Started | Founder / Solo Developer | 8 | AC-019 |  | No complex matrix yet.
BL-020 | Sprint 4 | 1.2 | Create communication log manual | Communication log | 0.18,1.1 | P1 | Not Started | Founder / Solo Developer | 10 | AC-020 |  | Manual entry only; no Gmail/Teams yet.
BL-021 | Sprint 4 | 1.3 | Create meeting notes screen | Meeting notes UI | 0.18,1.1 | P1 | Not Started | Founder / Solo Developer | 8 | AC-021 |  | Simple rich text optional.
BL-022 | Sprint 4 | 1.4 | Create decision log | Decision log | 1.2,1.3 | P1 | Not Started | Founder / Solo Developer | 10 | AC-022 |  | Decision must link to project.
BL-023 | Sprint 5 | 1.5 | Create document/evidence repository basic | Evidence repository | 0.10,0.18 | P1 | Not Started | Founder / Solo Developer | 8 | AC-023 |  | Supabase Storage or external URL.
BL-024 | Sprint 5 | 1.6 | Create traceability links table UI | Traceability links UI | 1.2,1.3,1.4,1.5 | P1 | Not Started | Founder / Solo Developer | 12 | AC-024 |  | At least decision-to-evidence and communication-to-decision.
BL-025 | Sprint 6 | 1.7 | AI extract decisions from meeting notes | AI decision extraction | 0.15,1.3,1.4 | P1 | Not Started | Founder / Solo Developer | 10 | AC-025 |  | Human confirmation required.
BL-026 | Sprint 6 | 1.8 | AI extract action items | AI action item extraction | 0.15,1.2,1.3 | P1 | Not Started | Founder / Solo Developer | 8 | AC-026 |  | Can save to action_items or notes if tasks not built.
BL-027 | Sprint 6 | 1.9 | AI summarize communication history | AI summary | 1.2,1.4,0.15 | P2 | Not Started | Founder / Solo Developer | 8 | AC-027 |  | Must cite linked records in app UI.
BL-028 | Sprint 7 | 1.10 | Create basic search | Basic search | 1.2,1.3,1.4,1.5 | P1 | Not Started | Founder / Solo Developer | 8 | AC-028 |  | Semantic search can come later.
BL-029 | Sprint 7 | 1.11 | Create MVP-0 project memory dashboard | Project memory dashboard | 1.2,1.4,1.5,1.6 | P1 | Not Started | Founder / Solo Developer | 10 | AC-029 |  | Dashboard answers: what happened, what was decided, where is evidence.
BL-030 | Sprint 7 | 1.12 | Add audit log for critical records | Audit logging | 0.10,1.4,1.5,1.6 | P2 | Not Started | Founder / Solo Developer | 8 | AC-030 |  | Critical for trust.
BL-031 | Sprint 8 | 1.13 | Manual end-to-end scenario test | E2E test evidence | 1.6,1.7,1.10,1.11 | P1 | Not Started | Founder / Solo Developer | 6 | AC-031 |  | Record screenshots or notes.
BL-032 | Sprint 8 | 1.14 | Performance and AI cost smoke check | Performance/cost notes | 1.7,1.8,1.9,1.11 | P2 | Not Started | Founder / Solo Developer | 4 | AC-032 |  | Simple spreadsheet or notes.
BL-033 | Sprint 8 | 1.15 | Prepare demo script | Demo script | 1.11,1.13 | P1 | Not Started | Founder / Solo Developer | 4 | AC-033 |  | Demo for validation interviews/design partners.
BL-034 | Sprint 8 | 1.16 | Deploy MVP-0 preview | Preview deployment | 0.17,1.13 | P1 | Not Started | Founder / Solo Developer | 8 | AC-034 |  | Shareable preview link.

## Acceptance_Criteria
Acceptance Ref | WBS ID | Acceptance Criteria | Validation Method | Done? | Notes
AC-001 | 0.1 | MVP-0 scope is explicitly limited to Project Memory & Decision Traceability; excluded modules are listed. | Document review | No
AC-002 | 0.2 | There is one official source-of-truth folder and duplicate docs are archived or marked deprecated. | Manual inspection | No
AC-003 | 0.3 | Definition of Done covers functionality, RLS/security, i18n foundation, manual QA, and demo readiness. | Document review | No
AC-004 | 0.4 | Repository exists with README, environment setup notes, and initial branch workflow. | Repo inspection | No
AC-005 | 0.5 | Next.js app runs locally without errors and displays a starter route. | Local run | No
AC-006 | 0.6 | Base UI layout uses ProjectOps360° branding and soft green theme consistently. | Visual review | No
AC-007 | 0.7 | next-intl is installed with EN/ES message files and at least one translated page. | Local run | No
AC-008 | 0.8 | User can switch language and UI text changes for available translations. | Manual test | No
AC-009 | 0.9 | Supabase project exists and app can connect with environment variables stored safely. | Connection test | No
AC-010 | 0.10 | Minimal MVP-0 tables exist through migrations and include organization_id where needed. | DB inspection | No
AC-011 | 0.11 | Unauthenticated users cannot access protected app pages; authenticated user can sign in/out. | Manual auth test | No
AC-012 | 0.12 | User belongs to an organization and queries are scoped to that org. | Manual/SQL test | No
AC-013 | 0.13 | RLS prevents a test user from reading another organization’s project data. | RLS test | No
AC-014 | 0.14 | RLS smoke test checklist or automated tests are recorded and repeatable. | Test artifact | No
AC-015 | 0.15 | AI calls go through server-side AI service and every call logs ai_runs metadata. | Code/DB test | No
AC-016 | 0.16 | AI provider keys are not exposed to client bundle or repository. | Security check | No
AC-017 | 0.17 | App shell has sidebar/header and protected navigation routes. | Visual/manual test | No
AC-018 | 0.18 | A user can create and view at least one project with default language. | Manual test | No
AC-019 | 1.1 | A user can create, edit, list, and delete stakeholders inside a project. | Manual CRUD test | No
AC-020 | 1.2 | A user can manually log a project communication with source, date, stakeholders, and summary. | Manual CRUD test | No
AC-021 | 1.3 | A user can create meeting notes linked to a project and attendees. | Manual test | No
AC-022 | 1.4 | A user can create a decision linked to project and source communication/meeting. | Manual test | No
AC-023 | 1.5 | A user can upload/register evidence and link it to a project. | Manual/storage test | No
AC-024 | 1.6 | A user can link communication/meeting/decision/evidence records and view the links. | Manual test | No
AC-025 | 1.7 | AI suggests decisions from meeting notes but does not save them until user confirms. | AI/manual test | No
AC-026 | 1.8 | AI suggests action items from notes/communications and user can accept or discard them. | AI/manual test | No
AC-027 | 1.9 | AI generates a concise project communication summary referencing existing records. | AI/manual test | No
AC-028 | 1.10 | Search returns matching communications, meetings, decisions, and documents by keyword. | Search test | No
AC-029 | 1.11 | Dashboard shows recent decisions, communications, evidence, and missing/unlinked items. | Visual/manual test | No
AC-030 | 1.12 | Create/update/delete of critical MVP-0 records produces an audit log record. | DB test | No
AC-031 | 1.13 | Full vertical slice is demonstrated: project → meeting → AI decision → evidence link → search. | End-to-end test | No
AC-032 | 1.14 | AI latency/cost and key page performance are measured and documented at least once. | Manual measurement | No
AC-033 | 1.15 | Demo script clearly explains the problem, workflow, and value of MVP-0. | Document review | No
AC-034 | 1.16 | Preview deployment is accessible and passes smoke test. | Deployment test | No

## Dependencies
Task ID | Task | Depends On | Dependency Type | Blocking? | Notes
0.2 | Create single source of truth folder | 0.1 | Finish-to-Start | Yes | Complete dependency before starting task.
0.3 | Define Definition of Done | 0.1 | Finish-to-Start | Yes | Complete dependency before starting task.
0.4 | Create project repo | 0.1 | Finish-to-Start | Yes | Complete dependency before starting task.
0.5 | Install Next.js + TypeScript app | 0.4 | Finish-to-Start | Yes | Complete dependency before starting task.
0.6 | Install UI foundation | 0.5 | Finish-to-Start | Yes | Complete dependency before starting task.
0.7 | Install next-intl | 0.5 | Finish-to-Start | Yes | Complete dependency before starting task.
0.8 | Create language switcher | 0.7 | Finish-to-Start | Yes | Complete dependency before starting task.
0.9 | Create Supabase project | 0.4 | Finish-to-Start | Yes | Complete dependency before starting task.
0.10 | Create baseline DB schema | 0.9 | Finish-to-Start | Yes | Complete dependency before starting task.
0.11 | Configure Supabase Auth | 0.9,0.5 | Finish-to-Start | Yes | Complete dependency before starting task.
0.12 | Implement organization membership model | 0.10,0.11 | Finish-to-Start | Yes | Complete dependency before starting task.
0.13 | Create initial RLS policies | 0.10,0.12 | Finish-to-Start | Yes | Complete dependency before starting task.
0.14 | Create RLS smoke tests | 0.13 | Finish-to-Start | Yes | Complete dependency before starting task.
0.15 | Create AI service abstraction | 0.10 | Finish-to-Start | Yes | Complete dependency before starting task.
0.16 | Configure AI environment variables | 0.15 | Finish-to-Start | Yes | Complete dependency before starting task.
0.17 | Create app shell navigation | 0.6,0.11 | Finish-to-Start | Yes | Complete dependency before starting task.
0.18 | Create project shell | 0.10,0.17 | Finish-to-Start | Yes | Complete dependency before starting task.
1.1 | Create stakeholder register basic | 0.18 | Finish-to-Start | Yes | Complete dependency before starting task.
1.2 | Create communication log manual | 0.18,1.1 | Finish-to-Start | Yes | Complete dependency before starting task.
1.3 | Create meeting notes screen | 0.18,1.1 | Finish-to-Start | Yes | Complete dependency before starting task.
1.4 | Create decision log | 1.2,1.3 | Finish-to-Start | Yes | Complete dependency before starting task.
1.5 | Create document/evidence repository basic | 0.10,0.18 | Finish-to-Start | Yes | Complete dependency before starting task.
1.6 | Create traceability links table UI | 1.2,1.3,1.4,1.5 | Finish-to-Start | Yes | Complete dependency before starting task.
1.7 | AI extract decisions from meeting notes | 0.15,1.3,1.4 | Finish-to-Start | Yes | Complete dependency before starting task.
1.8 | AI extract action items | 0.15,1.2,1.3 | Finish-to-Start | Yes | Complete dependency before starting task.
1.9 | AI summarize communication history | 1.2,1.4,0.15 | Finish-to-Start | Yes | Complete dependency before starting task.
1.10 | Create basic search | 1.2,1.3,1.4,1.5 | Finish-to-Start | Yes | Complete dependency before starting task.
1.11 | Create MVP-0 project memory dashboard | 1.2,1.4,1.5,1.6 | Finish-to-Start | Yes | Complete dependency before starting task.
1.12 | Add audit log for critical records | 0.10,1.4,1.5,1.6 | Finish-to-Start | Yes | Complete dependency before starting task.
1.13 | Manual end-to-end scenario test | 1.6,1.7,1.10,1.11 | Finish-to-Start | Yes | Complete dependency before starting task.
1.14 | Performance and AI cost smoke check | 1.7,1.8,1.9,1.11 | Finish-to-Start | Yes | Complete dependency before starting task.
1.15 | Prepare demo script | 1.11,1.13 | Finish-to-Start | Yes | Complete dependency before starting task.
1.16 | Deploy MVP-0 preview | 0.17,1.13 | Finish-to-Start | Yes | Complete dependency before starting task.

## Build_Risks
Risk ID | Risk | Likelihood | Impact | Severity | Mitigation | Owner | Status | Trigger | Response Plan
BR-001 | Scope creep from adding PMO/BPM/ERP/materials too early | High | High | Critical | Enforce MVP-0 wedge and MoSCoW exclusions. | Founder / Solo Developer | Open | New module requested before MVP-0 demo | Move to Later unless it directly supports traceability.
BR-002 | Solo capacity overload | High | High | Critical | Plan only 70% of available hours and protect buffer. | Founder / Solo Developer | Open | Sprint commitment exceeds planned capacity | Cut P2/P3 items from sprint.
BR-003 | RLS security defect | Medium | High | High | Create RLS tests in Phase 0 and run before deploy. | Founder / Solo Developer | Open | Cross-org data visible in tests | Block release until fixed.
BR-004 | AI output inaccurate or hallucinated | Medium | Medium | Medium | Human-in-the-loop, show evidence, require confirmation. | Founder / Solo Developer | Open | AI suggests unsupported decision | Reject suggestion and refine prompt.
BR-005 | i18n slows development | Medium | Medium | Medium | Implement foundation only; avoid full translation coverage until needed. | Founder / Solo Developer | Open | Translation catalog becomes blocker | Keep language files minimal for MVP-0.
BR-006 | Too many documents diverge | Medium | Medium | Medium | Single source of truth folder and archive old versions. | Founder / Solo Developer | Open | Multiple current specs conflict | Update source-of-truth and mark others deprecated.
BR-007 | Deployment configuration issues | Medium | Medium | Medium | Deploy early in Sprint 4 and document env variables. | Founder / Solo Developer | Open | Local works but preview fails | Create deployment checklist.
BR-008 | User validation delayed | Medium | High | High | Prepare demo script and start discovery early. | Founder / Solo Developer | Open | No design partner by MVP-0 completion | Use interviews and async demos to collect feedback.

## Data_Lists
Status
Not Started
In Progress
Blocked
Done
Deferred
Priority
P1
P2
P3
Sprint
Sprint 0
Sprint 1
Sprint 2
Sprint 3
Sprint 4
Sprint 5
Sprint 6
Sprint 7
Sprint 8
Later
Owner
Founder / Solo Developer
Phase
Phase 0
MVP-0
Languages
en
es